Key Performance Indicators and Annual Targets

| LINK Strategic Objective | Key Performance Indicator | Annual Target | Progress as at end of September 2009 Covering second quarter, July-Sept 2009 |
| --- | --- | --- | --- |
| Our focus as a facilitating network is very much around outcomes, e.g., numbers of briefings, submissions, meetings, workshops organized through LINK. We will continue to measure these. It is also important to try to measure impact, e.g. how our contributions are valued and seen to affect. We will survey perceptions of the impact of these contributions during the three years of the Corporate Strategy 2009-12. Results to be reviewed through the KPI reporting cycle. |  |  |  |
| 1. A Sustainable Scotland | Number and activity level of task forces. | Maintain at least 8 task forces which are actively addressing current policy priorities, each involving at least 3 member bodies and meeting at least 4 times a year | On target: Active TFs currently are Marine, SLUS, SOAs, Landscape, Agri, Bio, WNE Bill (incorporating Deer TF), Planning, as well as Parly Forum, SEFF, Landscape Climate meeting organized to take stock late Jan. |
|  | Number of collective position statements produced. | Produce at least 15 collective position statements (including policy and parliamentary briefings/consultation responses) with at least 5 member bodies signed up to each | On target. 7 policy outputs during October to December 2009 (Plus 15 policy outputs during April-June 2009) Outputs include written and oral evidence, briefings and a press release |
|  | Percentage of external stakeholder groups in which we are involved, relating to our key policy priorities, where LINK’s opinion is that the group has been valuable. | At least 40 | On target. |
|  | Number of face-to-face exchanges on agreed key policy priorities with decision-makers and opinion-formers facilitated by LINK core staff. | At least 25 face to face exchanges with MSPs facilitated by LINK core staff | On target. |
| 2. A Strong Voice for the Environment | Number of internal seminars/workshops/trainings on current issues arranged for members. | At least 3 workshops / seminars/ training days per annum | Target exceeded. Workshops in previous quarters were Sustainable Land Use Workshop, September 2009; Parliamentary Training Day, July 2009; WNE July 2009; Health, May 2009; and Access to Justice May 2009. |
|  | Percentage of member bodies involved annually in either the Board, Task Forces, or contributing to annual Congress. | At least 90% of member bodies involved annually in either the Board, Task Forces and steering groups or contributing to annual congress. |  |
| 3. An effective, efficient and accountable network | Quality of annual reports and accounts and returns in accordance with OSCR and Companies’ regulations. | Produce annual Trustees’ report and accounts, and annual return, in accordance with OSCR and Companies regulations. | On target. 2008-09 process completed successfully on-time. |
|  | Annual Operating Plan of network aspirations (with Member, Taskforce and Board input) is subject to regular review and six-monthly evaluation. | Network’s activity and aspiration captured, managed and evaluated with Board overview through annual operating plan, and learning applied. |  |
|  | The percentage of funding sourced from members for essential services holds steady or rises over the period at the level agreed to be equitable to members whilst maintaining autonomy and achieving objectives. | £69.6K subscription income target for 2009-10 (to achieve 48.8% of Essential expenditure) | Target exceeded. 2009-10 subscriptions will exceed the 50% target 12 months early. |

KEY to MAIN ACRONYMS and SHADING

| CO | Chief Officer (Jen Anderson) |  | ATF | Agriculture Task Force |
| --- | --- | --- | --- | --- |
| DO | Development Officer (Alice Walsh) |  | BTF | Biodiversity Task Force |
| PO | Parliamentary Officer (Andy Myles) |  | CTF | Climate Task Force |
| AFO | Administration and Finance Officer (Hugh Green) |  | DTF | Deer Task Force |
| AISO | Administration & Information Support Officer (Kate MacColl) |  | FWTF | Freshwater Task Force |
| PAO | Parliamentary Administration Officer (Susan Guest) |  | LTF | Landscape Task Force |
| MRO | Marine Research Officer (Alan Wells) |  | HTF | Proposed Health Task Force |
| TFCs | Task Force Convenors |  | MTF | Marine Task Force |
| Reps | The main Representatives appointed to LINK by the member organisations |  | PF | Parliamentary Forum |
| FSG | Finance Sub Group – Board and member Reps overviewing LINK’s finances |  | PTF | Planning Task Force |
| SEW SG | Scottish Environment Week Steering Group |  | SEFF | Scottish Environmental Fundraisers Forum |
| AAR | After Action Reviews |  | SOATF | Single Outcome Agreement TF |
| PSR | Political Strategy Report |  | SLU TF | Sustainable Land Use TF |
| ☺ | Status: On target |  | WNE BT | Wildlife and Natural Environment Bill Team |
|  | Status: Not on target |  |  |  |
|  | Status: Board discussions required |  |  |  |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE KPI 1.1 Number and activity level of task forces. Target Maintain at least 8 task forces which are actively addressing current policy priorities, each involving at least 3 member bodies and meeting at least 4 times a year. KPI 1.2 Number of collective position statements produced. Target Produce at least 15 collective position statements (incl. policy and parliamentary briefings/consultation responses) with at least 5 member bodies signed up to each. KPI 1.3 Percentage of external stakeholder groups in which we are involved, relating to our key policy priorities, where LINK’s opinion is that the group has been valuable. Target At least 40. KPI 1.4 Number of face-to-face exchanges on agreed key policy priorities with decision-makers and opinion-formers facilitated by LINK core staff. Target At least 25 face to face exchanges with MSPs facilitated by LINK core staff. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed. Who what, how, when? | Indicator of progress | Time scale | Scale of effort | Respon-sibility/ lead | Support | Status | Comments / Progress |
| 1.1 Share information amongst members on LINK's agreed key policy priorities to enable members to make informed and effective decisions | Ensure a task force or other mechanism is identified and functioning to develop joint position and engage effectively with externals, on issues prioritised by network. | Quarterly Networking involves mix of TFs, Reps, Trustees, Hon Fells, to ensure network is alive to opportunities for influencing wider agenda, prioritises with knowledge of resources to hand and required, and addresses gaps.(See Annual planning process at 3). | Autumn annual planning meeting involves representation at 85% of TF and Board and 65% of member bodies. | Q4 | med | Chair CO | TFCs, Reps, and specified Staff. |  | Oct 09 Board discussed internal structures for policy work / needs and explored with members in Nov 09. Nov 09 strategic planning noted various priorities, some of which are up and running at Jan 2010, others require to be discussed further or established. Jan 2010 networking will consider priorities again. |
|  | Network’s horizon scanning processes to be informed by intelligence of diverse members. | All players asked to flag up issues in advance of Annual Planning meeting. |  | Q3 | Med | Chair CO | TFs, Reps, Trustees, HFs, staff | ☺ | Most members & TFs submitted forward plans for discussion and consideration at Nov 09 strategic planning meeting. |
|  | Network develops and monitors political strategy. | Political Strategy Report developed in consultation across network and reviewed at least twice a year by Board and Networking meetings. |  |  |  | PO | Parly Forum, Trustees, TFCs | ☺ | 2nd PSR prepared for Board Oct 09 (reviewing our EU engagement esp) and policy priorities paper for Jan 2010. |
|  | Provide relevant information on developments of Scottish Parliament and Government. | Weekly report on forthcoming activity in Scottish Parliament (SP) with review of previous week’s action. | Weekly monitoring to Reps, Trustees, task forces. | ong | Med | PAO | PO | ☺ | Weekly monitoring continues with good feedback. |
|  | Pursue proactive membership of EEB and IUCN. | EEB/IUCN information monitored for monthly report to members with targetted flagging of particular opportunities. | Filter info to members and TFs monthly. |  | Low | PAO and JHughes (Trustee) | AISO | ☺ | Monthly monitoring has resumed after August break. Discussions held with English Link and Green Alliance in London re EEB-UK / Europe-level engagement. |
|  |  | Delegates to EEB and IUCN engage with member input and report back to members. |  |  | low | JHughes, SBrooks | PAO |  | Ongoing as capacity allows. |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks |  | Action needed. Who what, how, when? | Indicator of progress | Time scale | Scale of effort | Respon-sibility/ lead | Support | Status | Comments / Progress |
| 1.1 Share information amongst members on LINK's agreed key policy priorities to enable members to make informed and effective decisions | Screen incoming info for relevance to network. |  | Filter incoming material for monthly info bulletin and targetted emails to TFs and others. | Monthly bulletins and targeted alerts to TFs and Reps. |  | med | AISO | CO, DO | ☺ | During gap between IO leaving and AIO starting, CO produced bulletins in Nov and Dec, DO filtered emails. |
|  | Monthly bulletin Ensure membership is kept fully informed of the range and scope of LNK activities. |  | Update members on LINK activity, using data from TFs proforma info quarterly and reports from staff (post Board, party confs, events, projects, campaigns, etc). | Reps and TFs are circulated with information on current LINK activity and thinking, quarterly. |  | Med | AISO | TFCs Staff. | ☺ | Happened. |
|  | Newsletter | Newsletter compiled from LINK outputs and input of members/guests. Paper version copied inhouse and circulated. E-version for website, e-group. |  |  | Q1,2,4 | med | DO | Reps, Staff | ☺ | Prepared and circulated December. |
|  |  | TFCs identify where parliamentary and other support is required over next 18 months for autumn planning meetings. |  |  | Q4 | low | TFCs | TF members | ☺ | Ad hoc |
|  | Ensure staff support to TFs with Parliamentary focus, and that PO feeds relevant TF issues through Parliamentary Forum and PSR for coordination with parliamentary/political activity, integration, advice purposes. | Keep overview of LINK engagement with SP, over range of TF and politically focused activities for integration and organisation of comms, evidence, liaison meetings with parties, researchers, MSPs. |  | PO takes part in meetings of task forces with parliamentary focus, including parliamentary forum. Minutes available. | ongoing | High | PO | TF and PF members | ☺ | PO has attended and supported TFs as appropriate – together with SLUS, SOAs and other ad hoc groups. |
|  | Ensure feedback to members/network from events/initiatives at which the network is represented. | Delegate, staff or designated person report on meetings with Ministers, agencies, externals to inform other relevant parties in LINK and ensure integration. |  | Reports of ministerial meetings provided, put on website/ circulated. | Ongoing | Med | Identified lead. AISO, other Staff |  | ☺ | November date slipped to Dec when reps met with R Cunningham for discussion of SLU, SOA, agriculture, NPs, health/environment and more, led by Ian McCall with Jen Anderson and Andy Myles for staff. Note on website. 25 Feb in diary for next meeting. |
|  | Ensure devolution works for benefit of environmental agenda over UK | Contribute LINK views to ‘National Conversation’ and other key opportunities, to influence impact of devolution on environment |  |  | Q1 Ongoing | med | PO | Trustees, Reps | ☺ | Calman Commission given evidence early 09. Trustees and staff met with SG August and with Minister Dec 09. Reluctant to engage in debate on constitutional matters; indicated to Govt we will continue to engage around environmental stewardship, whatever the constitutional arrangements. |
| 1.2 Build consensus amongst members on key policy priorities | Members contribute to development of LINK positions by participating in the relevant TFs or wider workshops. | Reps review the importance of issues to their orgs and commit sufficient resources to deliver if part of that TF. |  | LINK positions integrated via TFs with each other, and with members’ own, via Reps. | ongoing | High | Reps |  |  | Staff cannot comment on this action. Staff have flagged benefit of more explicit planning of resources in structures paper to Oct Board and to Nov 09 strategic planning meeting. |
|  |  | Identify issues requiring consensus-building (see below for TFs who have). |  |  | Mainly Q4 | med | TFCs Reps | TFs | ☺ | Marine renewables is relevant; brief for commissioned work in prep at Jan 2010. |
|  |  | Annual planning and quarterly networking meetings identify, agree process, leadership. Staff support process. |  |  | Q4 and ongoing | med | Chair | CO and Staff, TFCs Trustees |  | IN hand for / from Nov 09 strategic planning, in relation to key issues identified. Some new TFs with convenors emerging. |
|  |  | Staff keep overview of TF outputs to advise if necessary on LINK protocols. Staff ensure protocols are clear and accessible on members’ website. |  |  | Ongoing | med | CO, DO, PO, PAO, AISO |  | ☺ | Ongoing. Protocols to be updated to clarify that co-options to TFs should go first to the Board for approval. |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed. Who what, how, when? | Indicator of progress | Time scale | Scale of effort | Respon-sibility/ lead | Support | Status | Comments / Progress |
| 1.2 Build consensus amongst members on key policy priorities | For 09/10 commitment for intertaskforce integration is: ATF: with BTF on SDRP, with CTF on climate and agric; land use consultation, food policy and soils strat with have overlap with other tfs. BTF: hold joint meetings with other TFs as needed. CTF: meet other TFCs and Board DTF: FWTF: HTF: LTF: work with BTF andCTF and others MTF: RAS on coastal access issues WNEgp: PTF: other TFs and members on SPPG, SEA and NPF SEFF: SOAs: WTF: | TFCs to contact relevant others during year. TFCs use network meetings to id issues and progress. |  | ongoing | high | TFCs | TF members |  |  |
| 1.3 Facilitate better communication between member bodies, their supporters, and the wider Scottish public including via media | Communicate all LINK positions in clear accessible language with short summary. | TF members and main Reps communicate agreed LINK positions within their orgs, communicating to own supporters via inhouse channels and in relation to relevant media work. | Joint policy message communicated to supporters (LINK profile is not sought). | Ongoing | med | Reps |  |  | Staff cannot comment on progress |
|  | Spokespeople for LINK to communicate collective positions to media and externals. | Adequate briefing to be provided by policy leader. |  | Ongoing | low | Designated leads | Staff | ☺ | Ongoing. Good MTF effort and coverage recently of marine report and LINK position. |
|  | Agreed positions are integrated with those of member orgs and communicated with their supporters. | TF members, main Reps communicate back internally, raise problems in good time. | Faultlines foreseen and joint positions clear. | Ongoing | med | Reps, TF members |  |  |  |
|  | Ensure all LINK positions are integrated with other LINK positions | Task forces to communicate with each other at and between network meetings to ensure complementarity /not contradiction. | Our policies are consistent and complementary | Ongoing | med | TF, Board | staff | ☺ | Networking discussions, and ad hoc comms by convenors and staff tend to identify particular needs. |
|  | Members and TFs regularly review and identify appropriate allies. | Considered at Annual Planning and quarterly Networking meetings. | LINK players engaged in comms activities of SCCS and other allies (eg health) on areas of joint interest. | Ongoing | low | TFCs Reps |  | ☺ | Up for discussion in November re priorities identified there. |
|  | Communications staff from relevant organizations coordinate media strategy where level of interest/benefit is appropriate. | Where relevant, TF members ensure comms coordination happens. | Staff support applies to current priority TF and project areas. | Ongoing | low | TFCs | TF member’ Comms Staff | ☺ | More good work recently between MTF, LINK staff and member body media staff, in relation to marine. |

| STRSTRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks |  | Action | Indicator of progress | Timescale | Scale | Resprresp lead ibility | Support | Status | Comments / Progress |  |  |
| 1.4 Advocate LINK's agreed key policy priorities to opinion formers and decision makers by identifying and acting on key opportunities to influence them | Maintain political strategy live to contexts and review at least twice yearly via Board and Networking |  | PO drafts PSR twice yearly for PF, then Board and Networking discussions. This is disseminated across the network. | Strategy reflects sound SWOT at various levels for Scot envt? |  |  | PO | Group of Trustees, convs | ☺ | 2nd PSR written, distributed October 09. Policy priorities paper for Jan 2010 networking. |  |  |
|  | Focus agendas for ministerial meetings on key policy priorities. |  | Consult network to identify key priority issues for ministerial meetings; identify delegates, arrange pre-meeting, provide supporting information. | Agendas relevant. Turnover of Reps from across network. | Q 1-4 | mmed | Chair CO | TFCs Reps Staff | ☺ | We try to ensure each agenda is topical and to be clear about the asks of / messages for the Ministers. Delegates etc identified and prepared in advance. |  |  |
|  |  |  | Liaison with ‘G6’ group to ensure integration of positions and updates to members. | Both series promote relevant joint positions. | Q1-4 | low | Chair, LWA, CO | NGO heads | ☺ | Liaison with G6 group is loose, but ongoing, so that there is some mutual understanding of each other’s agenda. |  |  |
|  | Hold regular meetings with party researchers and relevant spokespeople on key priorities. |  | Meetings with parties on future issues, legislation, communicate LINK positions on key priority areas (vision); and report to members. | Parties understand collective position on key issues, LINK influences theirs. |  | med | PO | TFCs Reps, | ☺ | Ongoing. |  |  |
|  | Continue to ensure effective ‘soft’ lobbying opportunities for members focussed mainly on MSPs and researchers. |  | On basis of 09 outcomes, start planning March 09 for Feb 10 event. Steering group proposes format, sponsors and maintains overview. Liaison with Parliament, sponsors, coordination of events and media work. Parl staff commitment high Sept - Feb. | SEW events supported by increasing number of MSPs. | Qs 3,4,1 | High | PO | CO, DO PAO SEW St Gp, Reps TFs | ☺ | SEW 2010 plans in preparation. |  |  |
|  |  |  | Individual seminar plans: Midweek Reception: Site visits in constituencies: Exhibition(s): Sponsors (financial and political): |  | In Q3 |  | Events organiser | PO, PAO | ☺ | SEW Timetable and plans update will be presented at Network and Board |  |  |
|  | Strategic use of party conference opportunities, to promote key network concerns. |  | Coordinate LINK presence at party conferences based on agreed function, form and funding. Organise materials, rota of members. Members participate and support costs. TFs lead on fringe events. | Attendance at confs, staging of fringe events on key issues. Member Reps participate. | Spring autumn | med | PO and PAO | Parly Forum membersTFs, PAO | ☺ | Attended SNP and Green conferences in Autumn. 2010 conferences discussed at PF |  |  |
|  |  | Hold parties to account on manifesto commitments. | LINK strategy devised via PSR process. Monitoring coordinated by PF in conjunction with TFs, Board, Reps. PAO records MSP/parties’ voting for monitoring records. | Process, resources, clear, for when needed. |  | low | PO | TFs, Reps, Parly Forum | ☺ |  | Rolling Manifesto proposal approved by Board in 2009. Drafting discussed at PF and proceeding. |  |
|  |  | Keep UK, EU and other international routes to environmental goals on our radar. | Keep Westminster, Europe and internat routes on agenda for Annual Planning and Networking meetings. | Dialogue with UK, EU political reps where important | Q4 | low | TFCs CO | PAO, EEB/ IUCN delgs | ☺ |  | On Parly Forum agenda for Jan. Met with Links, Green Alliance in September. Discussed with members Nov 09. |  |
|  |  |  | Election group to pursue Europe 2009 elections re particular issues /opportunities as resources allow. |  |  |  | PO | Election Group | ☺ |  |  |  |
|  |  |  | Election group pursues Westminster (09 or 10) elections re key issues relevant to UK political parties and securing discussion with manifesto writers. |  |  |  | PO | Election Group | ☺ |  | Staff visited London for discussion of 2010 election with GA and WCL. Preliminary plans for 2010 Westminster election hustings prepared and circulated. |  |
|  |  | Monitor Local Authority role in relation to Scotland’s environment | Assess delivery of strategic SD /env objectives via Single Outcome Agreements Develop critical indicators. Promote to LGov and SG. Monitor progress against these. Liaison with SSN, SG and CoSLA Consider green star awards LA. |  |  |  | SOA SGp | CO | ☺ |  | Meetings with various held autumn09 to inform LINK work. Strategic planning Nov 09 agrees minimum work programme. SOATF meets Jan to agree plan. LINK document to be published late Jan. Overview work, monitoring and further meetings with stakeholders are part of the plan. |  |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks |  | Action needed. Who what, how, when? |  | Indicator of progress | Time scale | Scale of effort | Respon-sibility/ lead | Support | Status | Comments / Progress |  |
| Agri TF Vision: Sustainable agricultural systems that project supplies of safe healthy food, protect natural resources and enhance wildlife, habitats and cultural heritage, and provide jobs in rural areas contributing to a diverse rural economy |  | Implementation of an SRDP which contributes to ATF’s goals for a sustainable agricultural sector that delivers the maximum possible environmental and other public benefits. |  | Continue to engage with stakeholder groups. Ensure that funding is not removed from Rural Priorities or environmental objectives (axis 2). Assist Government where possible with promotion of rural priorities. May hold event on CAP vision help with organisation may be required. May require funding | Examination of no.s of land mngrs entering relevant options in RPs and LMOs should give some ind of success. |  |  | TFC | ArchScot, B’life –Bumblebee CT, Butterfly CS, NTS, P’life, RAS, RSPB SWT. WTF. WWFs | ☺ | ATF submitted a response to the Pack Review into agricultural payments. This followed the LINK CAP vision and laid out LINK’s views on how funding should be distributed in the future. |  |
|  |  | Input into implementation of health check changes in Scotland to ensure that they are interpreted in a manner best suited to the Scottish environment. Continue lobbying for further CAP reform |  | Continue work on CAP reform through Scottish Government and European contacts. | Pillar 2 funding increased. |  |  | TFC |  | ☺ | With Wildlife & Countryside Link, LINK has arranged a meeting with George Lyon (MEP) who is writing a report for the European Parliament on the future of the CAP. |  |
|  |  | Input to review of cross compliance aiming to make current measures more effective and introduce new measures to replace envi benefits of set-aside. |  | Ensure place on stakeholder group when convened. | Replacement scheme introduced for set-aside. Better cross compliance measures. |  |  | dele |  |  |  |  |
|  |  | A Less Favoured Areas Support scheme from 2010 reformed to meet LINK’s objectives of public money for public goods. |  | Respond to LFASS consultation. | Recs from cons response taken into a/c. |  |  | dele |  |  |  |  |
|  |  | Scottish Government policies on climate change and agriculture that incorporate LINK views. |  | Input views to Scottish Government. |  |  |  | TFC |  |  |  |  |
|  |  | Scottish Biodiversity Strategy Rural Implementation Plan reflects LINK views. |  | Place on relevant working group. |  |  |  | dele |  |  |  |  |
|  |  | A land use strategy for Scotland that reflects LINK’s views |  | Input to consultation. April Network meeting agreed to hold workshop in summer 09 to prep input . |  |  |  | A Myles | SLUS SG. TFs | ☺ | ATF input to production of LINK doc on a Sustainable Land Use Strategy |  |
|  |  | A Scottish food policy which contains sufficient environmental objectives |  | Input to consultation. Contact with environmental “champion” for food policy development. |  |  |  | TFC |  |  |  |  |
|  |  | A soil strategy that includes measurable environmental targets |  | ?? |  |  |  | TFC |  |  |  |  |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed. Who what, how, when? | Indicator of progress | Time scale | Scale of effort | Respon-sibility/ lead | Support | Status | Comments / Progress |
| BiodTF Vision: Scotland’s natural heritage, on land and sea, is complete in its diversity, composed of fully functioning ecosystems and resilient to accelerated envi change. | Raise the profile of eNGO biodiversity conservation delivery in Scotland through the published report and continued presence at policy tables | maintain a presence through LINK reps at all relevant meetings. Parliamentary support will be required timescale to be clarified. | publication and continued presence on new biodiversity groups |  | high | TFCs deles | Members: P’life, SWT, RSPB, B’life, SAGS, SNW, WTS, JMT, But’fly Con, B’bee CT, MCofS | ☺ | The TF was represented on the SBS Action Co-ordination Group, the SBS Science Group and the Scottish Biodiversity Committee. The TF was also represented on some of the SBS ecosystem groups and on the SEL SOA group. Several members have had discussions with SNH about species action delivery in the SBS ecosystem plans. The TF met with the Scottish Government to discuss the Wildlife and Natural Environment Bill. Seminar with local authority LBAP officers planned before March 2010. |
|  | Ensure the new biodiversity delivery structures in Scotland are fit for purpose and delivering for Scotland’s biodiversity. | Continue to push for effective action at SBC and ACG | Cont presence. Diff to measure effectiveness of any resulting action |  | high | deles |  | ☺ |  |
|  | Demonstrate effective use of the ecosystem approach, alongside species and habitat conservation, on the ground to inspire others | Continue to provide examples of eNGO work on the ground that uses the full suite of approaches available for effective conservation | Number of case studies publicised |  | med | BTF member |  | ☺ |  |
|  | Work with Agri TF to influence SRDP so it delivers for biodiversity conservation effectively and efficiently | Joint lobbying with ATF to influence the SRDP as it rolls out. | No. of reps made to all relv cttees and resulting changes in SRDP (if any) |  | high | TFC |  |  |  |
|  | Maintain overview of biodiversity delivery at UK level and continue input to its coordination through BRIG | Continue to sit on BRIG and report back to BTF | Maintained presence at meetings |  | low | dele |  |  |  |
|  | Work with Joint Links to inspire govts to continue working to 2010 target and successor | Engage with BTFs in England & Wales to influence the post 2010 targets: mechanism not yet agreed. | UK has a new post 2010 target that everyone across UK is working towards |  |  | TFC |  |  |  |
| Climate TF Vision : For global climate change to be limited to 2 degrees through reductions in greenhouse gas emissions of at least 3% per year. | Ensure strong climate change targets and sustainable approach duty within Climate Change Bill | Submit written evidence to Bill. Feb 09. PO to support progress of CC Bill in Parl early 2009 | LINK priorities identified in Stage 1 report | Q1 | high | Clifton Bain | members RSPB, WWF WTS, RAS, JMT, NTS, MCS, P’life Sustrans LINK PO | ☺ |  |
|  | Develop LINK positions on: Energy (efficiency and effectiveness, demand management), Transport and Heat Consultations Copenhagen Comms | Finalise positions. Mini-campaign on chosen topic Q2and3 Possible £££ demands for publication and dissemination of any materials. Ongoing work to engage with and respond to consultations Letter from LINK member body Chairs to Gordon Brown. | Finalised position statements Decide on TF focus for Q2and3 Letter drafted and sign off secured. | Q1 Q2 | Med Med med | TFC TFC TFC |  |  |  |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed. Who what, how, when? | Indicator of progress | Time scale |  | Scale of effort | Respon-sibility/ lead | Support | Status |  | Comments / Progress |
| Deer TF Vision: sustainable populations of native species deer, playing positive roles in Scott ecosystems, contributing to rural economy | Lobby for new deer legislation. One opp is potential WNE Bill We are looking for new structures to deliver deer management planning with greater public engagement/interest. | Will need support of PO. |  |  | Ongoing to 2010 |  | TF C | Active mem RSPB, NTS, SWT, JMT, SNW LINK PO | ☺ | Main work revolves around the proposed Wildlife and Natural Environment Bill and reform of the Deer (Scotland) Act 2006. Met ScotGov in December on WNE bill issues re Deer. Ministerial meeting Jan re same. Awaiting consultation report from WNE Bill and stakeholder event. Preparing for evidence to Scottish Parliament in the New Year. |  |
|  | Input to DCS/SNH merger process via established Reference Group. Seek to maintain progress with joint working and priority sites process to meet SG favourable condition of SSSI targets. Input to sustainable deer mgmt pilots | Maintain 2-3 bi-lateral meetings with DCS. Attend DCS Deer Management Round Table. Meet with ADMG 1-2 times. |  |  |  |  | TFC |  | ☺ | Also involved with deliberations about proposed DCS/SNH merger as part of the Public Services Bill. |  |
| Freshwater TF Vision: Securing the achievement of WFD’s good ecological status by 2015 will ensure sustainable use of water resources and land management that enhances the status of the water environment | Influence the contents and the implementation of river basin management plans - RBMPs, if written and implemented properly, can make a significant contribution to the sustainable management of Scotland’s water resources and the well being of all aquatic environments. | Continue engagement with the National Advisory group and Area Advisory groups; Comprehensive response to the draft RBMPs (on consultation from Dec 08); Close engagement and dialogue with other relevant orgs and SEPA | RBMPs seeking to achieve good ecol status by 2015; Derogations used in approp manner only where req’d; Restoration of water env high on agenda for RBMPs |  |  | high | TFC, (SWT) |  |  | FWTF not currently active so RBMP action on hold. WWT sought interest from email group in meeting to gather Scottish perspectives to Feb 2010 CIWEM conference. WWT are interested in FWTF-type action. Discussions towards new FWTF may flow early 2010 from RAFTs’ membership of LINK, and RSPB staff appointment |  |
|  | Engage with /influence other WFD related research, strategies, policies - all relevant WFD research and policies (such as diffuse pollution regulations and environmental standards) can directly influence the implementation of WFD, and so make a significant contribution to SD | Engage with WFD research project as appropriate; Respond to SG consultation on WFD related policies Close liaison with SG and other relevant orgs. | All ‘gaps’ in legislation solved in time for 1st RBMP |  |  | med |  |  |  | Aim needs reviewed by any new FWTF which may come about during 2010. |  |
|  | Influence the Flood Risk Management (Scotland) Bill - FRM (Scotland) Bill will introduce a new framework for the management of flood risk, concentrating on sustainable methods of flood management, making Scotland more sustainable. | Continue engage with FRM adv grp and rel sub-groups.Advocate sustainable FRM, w’ emphasis on nat flood mgt to Gov, MSPs and others. Respond to call for written evidence FRM Bill; Engage w’ parly contacts throughout Bill process; Promote and advocate main asks of LINK leaflet: FRM bill A vital step for Scotland and the findings of LINK report on Natural Flood Mgt. Where poss, promote site visits. | LINK leaflet on Bill says the delivery of ‘sustainable’ approach to flood risk management Natural Flood Mgt recognised as a priority measure in flood mgt; Duty on all responsible to deliver measures on the ground. |  | Q1 | high | TFC |  | ☺ | Very good outcomes in terms of LINK influence on and outcomes of the legislation. |  |
|  | Ensure adequate controls of Diffuse Pollution and other damaging activities. Complex problem, needs addressed via multiple approach, such as regulation, support and advice. One of most damaging activities; if addressed well can make Scotland more sustainable. | Engage with SG, SEPA, SNH and others in promoting appropriate measures to address DP Advocate a package of measures to address DP with SG and others; Engage with SEPA’s work on priority catchments. | SG strategy on DP for long term options for mgt. Strat to incl. reg & vol measures, spprt & advice (cchmt officers) |  |  | high |  |  |  | Aim needs reviewed by any new FWTF which may come about during 2010. |  |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed. Who what, how, when? |  | Indicator of progress | Time scale |  | Scale of effort | Respon-sibility/ lead | Support |  | Status | Comments / Progress |  |  |
| Health TF Vision: | Identify whether there are ways in which LINK and members can help promote the links between health and environment. |  | Consult with LINK members, meet PfA, BTCV & others to develop thinking. Meet with agencies again. Determine appropriate action. Active involvement in relevant HEN and SG stakeholder groups |  |  |  |  | CO Helen Zealley, Ian McCall, | several member bodies | ☺ |  |  | Nov meeting with SNH and NHS HealthScotland held. offered them a SEW slot. Linkages between H & E raised at Ministerial meeting – RC offered to put in request for Parly debate. At Forward planning Nov agreed to underline H & E messages clearly across LINK’s advocacy work. |  |
| Landscape TF Vision: to promote the Eu Landscape Convention, and landscape as a priority concern for the Scottish Government | Make sure the principles and objectives of Charter 9dev’d with SLForum) embedded in the thinking and policies of all arms of government. |  | Contribute to consultations, proactively seek meetings with Govt and other stakeholders, work with other LINK TFs such Biodiversity and Climate |  |  |  |  |  | mems JMT Arch Scot, Buglife NTS RAS, MCofS SWLG, APRS & (Co-optees) | ☺ |  |  | Concerned over lack of SG progress on Scottish Landscape Charter despite interest from Roseanna Cunningham, due to former Minister of Environment (Michael Russell) concerns. Progress on this issue unclear. Approval of Beauly-Denny concerning most members on LTF and general concern over integration of landscape issues within LINK. |  |
|  | Pressing for adoption of landscape-scale approach by bods and gov insts in Scot for holistic view of env’t, better quality of life and better communities. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Marine TF Vision: healthy, productive seas that can sustain thriving coastal communities in perpetuity | Influence the content of the Scottish Marine Bill, ensuring that it includes good environmental measures to protect the marine environment and making possible a sustainable economy and clean, healthy and productive Scottish seas. |  | Series of 4 fringe events on the SMB at spring party confs 09 to influence and gain political allies, reinforce our messages ahead of the draft Bill being introduced to parl . Subject to funding from Fighting Fund) Meetings with MSPs, researchers, - primary target group. A LINK Marine campaign doc – comprehensive accessible guide to our views on the SMB, for fringe events, meetings with MSPs, researchers, etc. Will reinforce messages, be important tool in influencing attitudes and later votes and amendments. (Subject to MBFF funding) | Table of policy positions and tools No. of attendees and quality of discussion at events, political allies gained No. of meetings and outcomes Awareness of LINK’s views on SMB, amendments lodged, ultimately qual of leg |  |  | high | TFC | MTF members RSPB, MCS, WWFS, HWDT, NTS, WDCS, SWT. MRO, MCO, PO | ☺ |  |  | Good progress improving the SMB at Stage 2. Stage 1 debate: RAE Committee (RAEC) S1 Report supported many LINK key recs for improving Bill including duty on Ministers ‘to have regard to need to maintain and improve the health of the Scottish marine area’. S1 Parliamentary Debate reflected evidence of LINK, SAMS Recovery report commissioned by LINK and mentioned LINK and MTF org. Many RAEC members and other MSPs supported LINK arguments for improving Bill. SAMS rep’t quoted by all major parties. Stage 2: LINK made detailed briefings for 42 amendments (several probing amendments) of the passage of the SMB through Parliament; MTF worked with POs in MTF to liaise with clerks and MSPs in RAEC and researchers to get amendments tabled. Eight important LINK amendments taken forward by RAEC at S2 (incl SD general duty, duty to produce National Marine Plan, Duty to include marine objtvs, Incl ecosystem objectives, in the National Plan). Liaison continues during Stage 3 due to culminate with Parliamentary debate early Feb. Many MTF amendments not moved at S2 will be revisited at S3 and have good chance of being included in final Act. Work afoot on priority amendments for Stage 3. SNP conference attended by MTF players & PO.. |  |
|  | Influence content of the UK Bill with regards to overlap and effect on Scottish legislation – ensuring that together both Bills can deliver effective protection for all UK seas. |  | Liaison with Links, UK NGOS, W’minister, agencies. |  |  |  |  | MRO, TFC | TF | ☺ |  |  | Ongoing UK Act (2009) – WCL organised an event to celebrate passing of historic Act, which will deliver planning, licensing and MPAs 12-200nm around Scotland. Calum Duncan attended |  |
|  | Fundraise for project continuation ensuring that LINK has adequate resources to continue to campaign for a strong Scottish Marine Bill. |  | Liaison with trusts. |  |  |  |  | MTFC | TF | ☺ |  |  | Tubney confirm funding for 2010-13: EFF bid still going through. If successful we will recruit new Advocacy&Policy Officer, alongside Alan |  |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed. Who what, how, when? | Indicator of progress | Time scale | Scale of effort | Respon-sibility/ lead | Support | Status | Comments / Progress |
| Planning TF Vision: to ensure that the Scottish land use planning system contributes to a more environmentally sustainable society | Respond to Scottish Government consultation on new Scottish Planning Policy and associated Environmental Report | LINK response required by June 2009 – may be requirement for ongoing lobbying work with ScotGov, Parliament and other groups til final SPP produced late 2009. Staff help generating publicity on key issues, engagement with media, Govt and parliament may be required. Comms with BEFS, community groups, other NGOs, RTPI, Cosla | Response submitted, changes made to final SPP in line with LINK aims |  |  | TFC & Deputy | Member: AS, APRS, B’life,FOES, JMT, NTS, RAS, RSPB, MCofS, SAGS, SWT,WTS Other Link TFs & members | ☺ | Major progress was response to consultation on revisions to consolidated SPP in November - the TF had a number of concerns with the original proposed draft – particularly the sustainable development section. TF members, with invaluable support from the LINK PO, effectively lobbied govt officials and Ministers such that revised proposals are a significant improvement. This has been a major success for the TF. Without our engagement, there is a real possibility that sustainable development policy in particular would have been much weaker in national planning policy. Our response in Nov welcomed this significant improvement. Final version of SPP is expected early in 2010. TFC & DTFC met SNH in December. |
|  | Ensure implementation of NPF2 in line with LINK aims | Assess final published version of NPF2. Input from other TFs required . Help generating publicity on key issues, engagement with media, Govt and parliament may be required. Comms with BEFS, community groups, other NGOs, RTPI, Cosla, | NPF2 implemented in line with LINK aims |  |  | TFC & Dep |  |  |  |
|  | Consider how the effectiveness of SEA in delivering environmental benefits can be improved | PTF, other TFs to identify what output could be most effective – e.g. briefing document, etc. Help may be required to produce output material, briefing, etc. Input from other TFs required. Comms with SNH, SEPA, HS, community groups, RTPI, SEA practitioners. | Production of appropriate output, noticeable improvement in quality of SEAs |  |  | TFC & dep |  |  | Planning TF to take on SEA remit. |
| Wildlife and Natural Environment Leg E-Group aim: | Influence development of proposed Wildlife and Natural Environment legislation by Holyrood for 2010/11 programme | Comms; Keeping members and TFs informed. Members input to stakeholder forum. |  |  |  | NH EGroup LAustin | Members RSPB, JMT, WTS, MCoS, BCS, SNW, SWLG, NTS. PAO | ☺ | Response submitted for September deadline, following workshop for interested members, and coordination (thanks to Lloyd) of input from various including BTF, DTF. Ongoing watching brief by WNE e-group, in prep for legislation. Met Minister Jan 2010. |
| SEFF Vision: to encourage and facilitate partnership work between fundraisers in LINK; and allow them to share information, experience and understanding of sources of funding for Scotland’s environment | Continue to provide a networking forum for environmental fundraisers | Arrange quarterly meetings/venues/guest speakers. 4 meetings per year with an average of 2 external speakers per meeting. |  |  |  | TFC | SWT, RSPB, NTS, SNW, RAS, WWFS, WTS, JMT, AS, WWT, WDCS, MCofS, B’life, BBCT, BC, HWDT, CC, Sustrans, SAGS, FoES, P’life, MCS | ☺ | Meeting held 2 December. Discussed proposal to commission research on the financial and non-financial values of NGO’s to the Scottish Economy in terms of biodiversity, ecosystem services, heritage, etc. |
| Parliamentary Forum : a network for parliamentary and policy officers | Networking for support as well as coordination of network’s holding government to account, election-specific activity, party conferences. Informed by and informing LINK political strategy report. | LINK parliamentary staff participate /convene. LINK PSR discussed in draft by PF prior to Board and Networking discussions. |  | Ongoing | Med | PO | PAO Active members: | ☺ | Sept PF discussed draft PSR. Jan PF discussed political developments, elections / Hustings, rolling manifesto and spring conferences, and meeting dates for 2010. |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action | Indicator of progress | Timescale | Scale | Respons- ibility | Support | Status |  | Comments / Progress |
| 1.5 Build partnerships with relevant organisations to promote agreed key policy priorities more widely | Participate in stakeholder groups relevant to key priority areas to build support for environmentally sustainable outcomes. | TFs choose rep for areas of discrete TF interest; Delegates responsible for comms with members via e-groups or TFs. | LINK rep articulates /negotiates case for LINK positions | Ongoing | med | Dele- gates | TFs, Constit- uencies of interest within LINK, |  |  | LINK is still actively involved in around 60 stakeholder forums. Due to difficulty of getting feedback from stakeholders on value of forums – originally intended to inform critiques of SG - staff propose dropping formal feedback requirement for production of annual analysis. LINK will continue to maintain list of groups and delegates, for information. |
|  |  | For wider issues AISO facilitates process of delegate election and feedback with interested members/TFs. | As above | Ongoing | med | AISO | Staff, Trustees. | ☺ |  | Ongoing |
|  | Pursue Climate Bill work in conjunction with SCCS Bill Team as far as possible | Climate TF promotes shared asks with and via SCCS TF complements with back-up on key env issues. PO involvement in SCCS Bill Team 2009. | LINK climate positions, comms and SCCS positions are joint or complementary | Ongoing | med | Climate TFC PO | CTF members in SCCS PO, | ☺ |  | CC Act passed in 2009. PO continues to engage with SCCS and contribute. |
|  | Include non-LINK interests in seminars, workshops, congress, SEW, festive reception. | Networking meetings identify potential allies for work areas. TFCs ensure liaison with identified allies. Staff ensure inclusion in wider LINK events. | LINK TFs work with others on wider joint positions. | Ongoing | med | Events Organisers | Staff, TFs | ☺ |  | Good spread of interests at Congress, festive reception. |
|  |  | Some actions to be followed up after Access to Justice workshop in May. |  |  |  |  | CO, PO | ☺ |  | No progress, due to capacity issues |
|  | Liaise with national organisations (of any sector, including other Links) which have overlapping agendas, to build case for environmental sustainability. | Annual high level meetings held with SNH, SGovt, SEPA, CoSLA. Ad hoc requests from others (eg Parks) are pursued. Coordinated by staff with input from TFs, Board and members. |  |  | low | Chair, CO | Staff |  | ☺ | Date for high-level meeting with SNH sought – no response yet. Met SEPA Oct 09 and due to meet again spring 2010. Other contacts via TFs. |
|  | The other Links | Maintain regular Joint Links liaison by telecon, for info-exchange and to identify areas where joint work useful. |  | Ongoing | low | CO | AISO, PO |  | ☺ | Ongoing. Telecon on generics + updates late October. Links propose joint seminar in NI September 2010 |
|  |  | TFs exchange plans with those of other Links. TFs watch for joint work opportunities (eg Climate, Bio, Marine, EEB UK liaison) for 2009 onward. |  |  |  | TFCs JHughes | MRO, MCO |  |  | Staff cannot comment, though do not see much evidence recently, except in marine where some interface is required for Bills and for project funding. ATF seeking input from other TFs for updating CAP vision doc. Scottish LINK strategic planning outcomes exchanged with Links Jan 2010. |
|  | SCVO | Participate in Intermediaries Network if issues in common. Rejoin SCVO Pol Cttee at 2009 SCVO Green Officer liaises with LINK on SD related areas Liaison over SOAs work? |  |  |  | CO & PO |  |  | ☺ | No engagement over last 6 months, though email comms and meetings with SCVO Green Officer re carbon, climate, and other areas in common. SCVO propose green reference group to take soundings across sector on upcoming issues. |

| STRATEGIC OBJECTIVE 1 : MAKING SCOTLAND SUSTAINABLE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action | Indicator of progress | Timescale | Scale | Respons- ibility | Support | Status | Comments / Progress |  |
|  | Other Bodies | TFs hold liaison meetings with as needed. TFs to regularly liaise with SNH contacts for info and mutual support in approaches. | Other orgs understand, and may support, LINK positions |  |  | TFCs | CO, DO, PO, AISO | ☺ | Deer, Planning, Biodiversity TF liaison with SNH this Q |  |
| 1.5 Build partnerships with relevant organisations to promote agreed key policy priorities more widely | Agriculture TF | Existing partnership working well, incl SNH, SCF, FWAG, SAC, NFUS, HIE, SCVO. Likely to progress through joint work ing on CAP Health Check issues, RDC imp, and LFA reform. |  |  | Ongoing | ATF C and deles to stakeholder groups | ATF members. | ☺ | SGov feedback for grant meeting Nov highlighted value of LINK reps on Agric forums |  |
|  | Deer TF | Close working with SNH and DCS Board members, liaison with ADMG, MoorlandForum, SRPBA |  |  | Ongoing | DTF C |  | ☺ | Good liaison, ongoing. |  |
|  | Freshwater | TF has contacts with various orgs and individuals. Close liaison with SNH on all fronts. Works with EEB, other Links |  |  | Ongoing | FTFC |  |  |  |  |
|  | Health | Participation in HEN Meet SNH, FC and other agencies Sept |  |  | Ongoing Q2 |  |  | ☺ | 2 delegates to HEN – are they active? Met SNH Sept, took discussions as far as possible, requested Ministerial support (who proposes to bid for a Debate), offering SEW event. |  |
|  | Landscape | Considering clear need for some wider network to impl Scot Landscape Charter and implement the Eu Landscape Convention even if Ministerial support will not fund secretariat of a forum |  |  |  | LTF |  |  |  |  |
|  | Marine |  |  |  |  | MCO | PO | ☺ | Met regularly with RAEC MSPs and researchers from SNP, Labour, Lib-Dem, Conservatives and Greens in advance of the S1 debate and prior to the three RAEC meetings considering the SMB at Stage 2 to outline the rationale behind proposed LINK MTF amendments. Met SG to clarify amendments at S2. Marine officials helpful at S2. |  |
|  | Planning | SNH, SEPA, HS, community groups, RTPI, CoSLA, SEA practitioners |  |  |  | PTF |  |  |  |  |
|  | WNE group |  |  |  |  |  |  | ☺ |  |  |
|  | SEFF | close liaison with SNH |  |  |  | SEFF con |  | ☺ | Ongoing |  |
|  | Hold annual festive reception for all LINK players and contacts for networking. | Staff book venue, catering, speakers, circulate invites, with input from TFs and others. | Event well attended. | Q3 | med | PAO | Staff, TFCs | ☺ |  |  |

| STRATEGIC OBJECTIVE 2: A STRONG VOICE FOR SCOTLAND'S ENVIRONMENT MOVEMENT KPI 2.1 Number of internal seminars/workshops/trainings on current issues arranged for members. Target At least 3 workshops / seminars/ training days per annum. KPI 2.2 Percentage of member bodies involved annually in either the Board, Task Forces, or contributing to annual Congress. Target At least 90% of member bodies involved annually in either the Board, Task Forces (and steering groups) or contributing to annual Congress. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective |  | Tasks | Action |  |  | Indicator of progress |  | Timescale |  | Scale |  | Respons- ibility |  | Support | Status | Comments / Progress |  |
| 2.1 Build capacity within the network to increase the effectiveness of member bodies working together as LINK |  | Encourage member bodies to take part in relevant areas of LINK work to reflect their interests. | Induction for new member Reps to cover all engagement opportunities. |  |  | New member bodies join at least one work area. |  | Ongoing |  | low |  | Chair, CO |  | TFs, Reps Staff |  | RZSS and RAFTS due. |  |
|  |  |  | Send timely reminders to members of upcoming opportunities to engage. Update website. |  |  | All member bodies involved in some area of LINK work over a year. |  | Ongoing |  | low |  | CO |  | IO and other Staff | ☺ | Ongoing via bulletin and email alerts as well as web updates. |  |
|  |  |  | Outreach to member bodies whose engagement in TFs and at core meetings is rare. |  |  | Non-engagers engage and/or better understand opportunities. |  |  |  |  |  | CO |  | Other staff | ☺ | Time has not allowed for much proactive outreach. Staff provide such organizations with as much phone / email feedback as possible. |  |
|  |  | Strengthen capacity and confidence of members to engage in public policy development through information exchange and policy workshops | Organisers ensure meetings, seminars, TF discussions are open to all members, with briefings pitched at appropriate level and contributions sought for overall positions. Staff assist comms for work outwith TF areas. |  |  | Use of Congress for mutual briefing. Provision of at least 1 or 2 workshops pa: 1. Access to Justice (May 2009) |  | Ongoing |  | med |  | Chair Staff |  | TFs and Staff | ☺ | Congress 09 helped achieve this ambition. |  |
|  |  |  | Active members of TFs share the representation at external events and on forums. |  |  |  |  | Ongoing |  | low |  | TFCs |  | TF members |  |  |  |
|  |  | Hold training events for members to build capacity in key areas (eg media, campaigns, parliamentary). | Board/TFs identify training needs. Staff organise and assist process. |  |  | Members take part and find trainings useful. Convenor session 2009? |  |  |  |  |  | Chair, CO |  | Staff, Reps | ☺  | Fundraising training day 18 Jan Convenor session? Idea abandoned. |  |
|  | Experienced TF members encourage others to take on responsibility for convening, representation. |  |  | All members of TFs need to commit adequate time towards the TFs’ work. | Effort well spread amongst all members in TFs. |  | Ongoing |  |  |  | TFCs |  | TF members |  |  |  | Nov 09 discussions indicate convenors continue to feel stretched. A general encouragement to the memberships of all TFs was noted, to share the overall workload as far as possible. |
| 2.2 Facilitate active involvement of member bodies in LINK's activities | Encourage wide involvement of members as Trustees, convenors or deputies, delegates to external forums, participants in steering groups for SEW, Congress and other areas. |  |  | By each April Board has considered mix of Trustees/skills; encourages turnover for good balance of organizational and professional experience. Staff ensure Reps know of opps. TFs appoint conv, dep, deles to share load and opportunity. | 80% of members to be involved in some leadership capacity over 3 year period. turnover in Board, Convenor and Depute representation |  | Q2 |  | Med |  | Chair and CO at 2009 esp |  | TFCs Trustees Staff |  | ☺ |  | Ongoing Jan 2010 Board will consider skills gaps in relation to places on the Board available from AGM 2010. Treasurer succession confirmed (Paul Ritchie SWT) for June. Volunteers for Congress steering group sought for spring 2010. |

| STRATEGIC OBJECTIVE 2: A STRONG VOICE FOR SCOTLAND'S ENVIRONMENT MOVEMENT |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action | Indicator of progress | Timescale | Scale | Resporesp lead | Support | Status | Comments / Progress |
| 2.2 Facilitate active involvement of member bodies in LINK's activities | Member bodies recognise that time spent on LINK activities is value for resources expended. | Trustees liaise with NGO heads to promote benefits of joint working and acknowledge contributions. Planning meetings rigorous in identifying resources and responsibilities for delivering these. | LINK TF work is given person time by member bodies | Ongoing | med | Trustees | Heads of members bodies | ☺ | Oct 09 Board advises engaging with CEOs where there are relevant agendas |
|  |  | Ensure LINK comms to members highlight achievements and acknowledge diverse inputs (annual review, bulletins, PSR, newsletter, website). |  | Ongoing, Q2, 4, | med | DO | Staff | ☺ | Annual review shown at Congress and Festive reception, & circ’ed to members. |
|  | Use annual members congress to build community within the network | Steering group develops theme for autumn Congress by late spring. DO to organise and publicise with members. Review of year's highlights to be prepared. | 70% of members participate in Congress annually, with involvement of all over 3 years | Q3,4 | med | Congress St.Grp, DO | Staff, Reps | ☺ | 74% members attended some part of Congress/Forward planning. |
|  | Ensure members know of annual cycle (4 meetings) and wider opportunities to engage in the network. | Notices and agendas go to Reps and Convenors. Dates maintained on website. Outreach promotes cycle and the opportunities input offers to influence network plans. | Increased member Reps at annual planning meetings | Ongoing | low | CO AISO CO | Staff | ☺ | Ongoing and quite healthy |
|  | Influence development of conducive funding environment for eNGOS. | SEFF and other advocacy. | SEFF meets range of funders (see SEFF reports). | Ongoing | low | Chair, SEFF TFC | Trustees, eNGO heads | ☺ |  |
| 2.3 Use targeted campaigning to encourage wider public support where important | Develop effective campaigns where appropriate | Needs and opps considered by all players for annual planning meeting, identifying resources and leadership | Annual planning identifies achievable campaigns in good time |  | high | TFs, PF, Reps |  | ☺ | Ongoing in the context of steering group and TF and political / policy discussions |
|  |  | If outwith planning cycle Board and network to endorse. |  |  |  | Chair |  |  |  |
|  | Marine campaign underway until Scottish legislation through and begins to be implemented | MTFC line manages MCO and MRO who are supporting work of the MTF. MTF-wide effort around 3-year re-application at spring 09 |  | Ongoing | High | MTF C | MTF, MRO, MCO, CO, PO, AFO | ☺ | Ongoing, good progress, with planning in hand for a phase 4, bid in prep, full cost recovery included. Recruitment for a second project officer could go ahead Dec/Jan. |
|  |  | CO, AFO provide support liaising with funders, reporting, HR, financials and project development. |  | Ongoing | low | CO, AFO | MTF C | ☺ | Ongoing support in place |
|  |  | LINK PO supports MCO wrt parly advocacy. |  | Ongoing | med | MTFC | PO | ☺ | Ongoing. |

| STRATEGIC OBJECTIVE 2: A STRONG VOICE FOR SCOTLAND'S ENVIRONMENT MOVEMENT |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action | Indicator of progress | Timescale | Scale | Resporesp lead | Support | Status | Comments / Progress |
| 2.3 Use targetted campaigning to encourage wider public support where important | Encourage behaviour change in relation to the climate challenge – via resonant, achievable messaging suitable to the range of members on issues with significant carbon emissions | Members develop behaviour change comms with memberships, monitor for reactions. | May comms meeting to develop messages with experts. Promote messages with members and offer 1:1 discussions. Find out SG timetable and plans for CC bill impl. to focus members’ messaging – coordination task | Q1 Q1,2 Q1,2 | Med Med med | DBarlow SG Reps Climate policy officers, SGroup | CO, St Grp Board |  | Workshop, with experts, last discussed a year ago. Lack of leadership, shortage of staff time and changes in members personnel have all conspired to hold up progress. Board Oct 09 agreed there are opportunities. Further discussion planned (MR/AM) to develop. |
|  |  | LINK inputs to Climate Alliance and Fund via delegates. |  |  | med | Deles | Board | ☺ | Ongoing |
|  |  | Carbon accounting |  |  | med | Board /CO |  | ☺ | LINK accounts. LINK Chair to re-encourage members early 2010, in wake of SCVO initiative, using LINK spreadsheets, to promote to sector. |
|  |  | LINK revises environmental policy |  |  | med | Board/CO |  |  | CO to liaise with various trustees, to update |

| STRATEGIC OBJECTIVE 3: AN EFFECTIVE, EFFICIENT, ACCOUNTABLE NETWORK KPI 3.1 Quality of annual reports and accounts and returns in accordance with OSCR and Companies’ regulations. Target Produce annual Trustees’ report and accounts, and annual return, in accordance with OSCR and Companies regulations. KPI 3.2 Annual Operating Plan of network aspirations (with Member, Taskforce and Board input) is subject to regular review and six-monthly evaluation. Target Network’s activity and aspiration captured, managed and evaluated with Board overview through annual operating plan, and learning applied. KPI 3.3 The percentage of funding sourced from members for essential services holds steady or rises over the period at the level agreed to be equitable to members whilst maintaining autonomy and achieving objectives. Target Funding subgroup’s spring 09 target of £67306 for subscription funding achieved by financial year end. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks | Action needed | Indicator |  | Timescale |  | Scale |  | Respons- ibillity |  | Support | Status |  | Comments / Progress |
| 3.1 Ensure LINK is well governed and managed in line with good practice | Board overview maintained of progress against LINK corporate strategy and annual operating plan. | Live operating plan reported on and reviewed by Board each quarter Identified leads provide data for monitoring - staff collate, and post on website quarterly. Board use to check integration and consensus –tactics resources New proposals assessed in this context by Board. Decisions between relative priorities by Board & Networking. OP updated as agreed. |  |  |  |  | med |  | Chair Chair Chair |  | Trustees, CO, DO and other Staff |  |  | Quarterly discussion due Jan 10. Draft OP for 2010/11 in prep, drawing on strategic planning meeting Nov 09. |
|  |  | KPI performance assessed quarterly by Board. |  |  | Ongoing |  | med |  | Chair/CO |  | DO, AISO, PO, PAO, id’d leads | ☺ |  | Ongoing |
|  | Hold annual autumn planning meeting to plan next 18 months’ network activity, ensuring an integrated approach to key strategic priorities. | Members and task force representatives and other identified project leaders to attend and contribute | High level of member ptcpn. |  | Q3/4 |  | med |  | Chair (CO) |  | Reps, DO, AISO, PO, | ☺ |  | Good attendance from members and TFs |
|  |  | Needs of environment and opportunities analysed, fresh approaches considered, by good horizon scanning process. |  |  | ongoing |  | high |  | Chair, CO |  | PO, PF, TFCs, Reps, Board, HFs | ☺ |  | Achieved November 09; further assessment of priority proposed (AM paper) for Jan 10 |
|  |  | TFCs and identified leads to ensure discussion of workplan Jul or Aug to return to staff end Sept. |  |  | Jul or Aug |  | med |  | TFCs and identified leads |  | Staff |  |  | Several TFs responded within timescale. |
|  |  | Staff arrange venue, agenda, papers, action points |  |  | Q3/4 |  | low |  | CO |  | DO, AISO, | ☺ |  | Done |
|  |  | Staff facilitate integration /workshops arising from the meeting TFCs pursue particular integration points |  |  | Q4/1 |  | med |  | CO TFCs |  | Staff, TFs, Trustees Staff | ☺ |  |  |
|  | Hold 4 Board meetings a year for Trustees to maintain strategic overview of LINK's direction and advise on operations, resources as required. | Trustees to attend, contribute and follow up actions as necessary. CO and other staff attend, note and follow up actions as necessary. | all board meetings held quarterly |  | Q1,2,3,4 |  | low |  | Chair |  | Trustees, Staff | ☺ |  | Ongoing – on track |
|  |  | CO prepares agenda in consultation with Chair with input from others as necessary. |  |  | ditto |  | med |  | CO |  | Chair, PO, DO, AFO | ☺ |  |  |
|  | Hold 3 Network meetings & annual planning meeting | Prepare agendas, invite input, representation. Report of meeting disseminated (web). Follow up agreed actions. |  |  | Qrly Qrly Ong’g |  | Low Low Med |  | CO O/DO TFCs, Reps Staff |  |  | ☺ |  | Ongoing – on track |
|  | Administer LINK's day-to-day finances, including Restricted and Designated funds Regular financial overview of network operations Produce Trustees’ report and accounts for OSCR and companies return for Companies House. | Manage financial ledger, for expenditure, invoicing, banking, payroll and pensions, project finance reports and supporting spreadsheets. Appropriate liaison with accountant, Treasurer, FSG. Submit required information on time. | Accounts pass Audit. Projects end in budget and Pos’ve Audit |  | Ongoing |  | High |  | AFO |  | FSG | ☺ |  | Ongoing – on track |
|  |  |  |  |  | Ongoing |  | Med |  | AFO |  | Staff Proj Mgers | ☺ |  | Ongoing – on track |
|  |  | Budget outturn and forecast prep to month end preceding Board meeting (except June where outturn to end June emailed to Trustees July), where appropriate checked with accountants and Treasurer before circulation to Trustees. | Outturns ratified by accountants, Treasurer and Board |  | Q1,2,3,4 |  | High |  | AFO |  | Treasurer for Board | ☺ |  | Ongoing – on track |
|  |  | Close off accounts 31/3, liaise with auditor to sign off and circulate to members 3 weeks before AGM. Draft narrative for Trustees to sign off. Submit to OSCR, accountants to Co House. | KPI 3.1 app by OSCR & Co House. |  | Q1 |  | High |  | AFO CO AFO |  | Chair, Treasurer, Staff. | ☺ |  | 2008-09 closed off successfully. 2009-10 on track |
| STRATEGIC OBJECTIVE 3: AN EFFECTIVE, EFFICIENT, ACCOUNTABLE NETWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual Objective | Tasks | Action needed | Indicator |  | Timescale |  | Scale |  | Respons- ibillity |  | Support | Status |  | Comments / Progress |
| 3.1 continued - Ensure LINK is well governed and managed in line with good practice | Board funding subgroup overviews financial issues. | AFO facilitates regular FSG contact to review all aspects of LINK’s financial and fundraising needs, coordinating 3-4 annual FSG meetings (Trustees, CO and DO). | Meetings happen; KPI 3.3 |  | Q1,2,3,4 |  | Med |  | AFO, Treasurer |  | CO, DO, FSG | ☺ ☺ |  | Last FSG meeting 10th Dec. KPI 3.3 achieved one year early. |
|  | Standing Board employment subgroup overviews HR issues. | CO or ESG prompt discussion as needed in relation to HR issues (policy, salary, grievance) and recruitment issues (where necessary) |  |  | Ongoing |  | low |  | CO, ESG |  | Trustees | ☺ |  | Admin & Info Support Officer appointed early Jan 2010 (Kate McColl) to Perth office. |
|  | Standing Operating Plan subgroup advises on production / reporting / analysis of OpPlan | CO prompts meeting of group during drafting of each annual plan |  |  | Q4 |  |  |  | CO |  | Staff, Trustees | ☺ |  | Not yet prompted. |
|  | Ensure match between LINK plans (ie TFs/projects), the resources required, and commitment from members to deliver these | Board to request members to commit £s person-time at annual planning time. Board to maintain overview. |  | Q4 |  |  |  | Chair/CO |  |  |  | ☺ | More effort to explore this at recent meetings with network. Useful. Board should keep under review. |  |
|  | Retain flexibility to react to new events, seize new opportunities | Board to evaluate new ideas, incorporating into Op Plan (if not at Annual planning time) |  | Ongoing |  | low |  | Chair/CO |  | Idea generator |  | ☺ | Board level ‘eye’ will be required on 20 November and thereafter |  |
|  | Audit of Trustees' skills maintained; Trustees share Board workload. | Trustees complete skills chart annually. Chair leads annual review to address significant gaps, share tasks ahead and plan for succession. | Trustees’ expertise cover areas of need |  |  | low |  | CO Chair |  | Trustees |  | ☺ | On target for Jan 2010 meeting |  |
|  | Trustees have 1:1 with Chair annually | Chair holds 1:1s with all Trustees annually, identifying if training or development needed. |  |  |  |  |  | Chair |  | Trustees |  |  | Ian plans to talk with Trustees during the coming quarter. |  |
|  | Risk analysis maintained to assess threats to optimum operation of network. | Chair/CO to prompt staff and Trustees to contribute to annual RA process. Chair to facilitate discussion of appropriate contingencies. Annual. | Trustees aware of potential threats and actions needed |  |  | low |  | CO |  | Trustees, Staff, TFCs Delegates |  |  | CO reviewing and will flag issues for discussion at January Board. |  |
|  | Induct new Trustees and member Reps to LINK | CO and Chair organise induction process and identify who takes part. | Trustees /Reps inducted within 2 months |  |  | low |  | Chair |  | Staff |  | ☺ | JA and John Mayhew arranged induction for Vicky Junik in July John Mayhew and JA met Ian McCall July for induction to chair role. |  |
|  | Support for Chair | CO, Trustees, TFCs and other staff provide briefings, drafts, back up for chair as required. |  | Ongoing |  | med |  | CO |  | Staff, Trustees |  | ☺ | CO & PO met Chair autumn. Regular phone / email contact ongoing. |  |
|  | Support for President | Chair, CO, staff, Trustees, TFCs etc to provide briefings, drafts, back up as required |  |  |  | med |  | Chair/CO |  | TFCs Staff, Trustees |  | ☺ | Ongoing – mainly by email, phone. |  |
|  | Ensure LINK operations are carried out in an environmentally sustainable way | LINK Board policy to be revised spring 2009, to inform staff, convenors and others responsible for action under LINK name. All organising LINK events follow policy wrt transport, procurement, venue choice, catering. Network’s procurement of services and goods to prioritise local, recycled, fairtrade, renewable. |  |  |  | low |  | Chair CO |  | CO, all Staff, Trustees, TFCs |  |  | No progress with updated policy. Existing policy is reasonably good. |  |
|  |  | LINK monitors own emissions on core business. | Emissions reduce |  |  |  |  | AFO |  | staff |  | ☺ | 2008-09 data published. Increased level of detail tracked for 2009-10, report due with Annual Report in April/May. |  |

| STRATEGIC OBJECTIVE 3: AN EFFECTIVE, EFFICIENT, ACCOUNTABLE NETWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Objective | Tasks |  | Action needed | Indicator | Timescale | Scale | Respons- ibillity |  | Support |  | Status |  | Comments / Progress |
| 3.1 continued - Ensure LINK is well governed and managed in line with good practice |  |  | Staff workplans are notified to members and TFs via website. |  |  |  | CO, AISO |  |  |  | ☺ |  | Staff feel members unlikely to read this level of detail. New site will list staff’s key responsibilities. Staff PDRs mainly completed at Sept 09 |
|  |  |  | Full team meetings organised by CO at least 6-weekly; chairing and notes by rotation. |  |  |  | CO, Staff |  |  |  | ☺ |  | Yes, ongoing every 6-7 weeks, with notes exchanged. Also useful database training day to be repeated annually as an IT day. |
|  |  |  | One-to-one meetings are held at least monthly between staff and managers - notes exchanged. |  |  |  | Line mgers reg1:1s |  |  |  | ☺ |  | Ongoing with notes exchanged |
|  |  |  | Monthly catch-ups held amongst Perth staff – notes exchanged. |  |  |  |  |  |  |  | ☺ |  | Re-established now after gaps for various reasons at both offices. |
|  | Provide training as appropriate. |  | Trainings and development needed to carry out the jobs agreed in discussion between staff and managers and provided mainly out of house (via SCVO, ACOSVO, etc). |  |  | low | Staff member |  |  |  | ☺ |  | Staff training on new website Jan, with PAO delivering. |
|  | Ensure TFs work comfortably to annual Operating plan. |  | TFs report progress against plan to Board quarterly for review flagging slippage, change of direction, concern. |  |  | med | Chair |  | Staff |  | ☺ |  | Ongoing |
|  | Hold AGM, elect Trustees and office bearers, appoint president. |  | Members to be advised of vacancies for Board in April / with first notice. CO prepares, circulates papers to members at least three weeks in advance. DO arranges field visits (unless AGM is tied to additional event). | Quorum of members participate, elections held, healthy rotation of board. |  | low | Chair |  | CO, Staff |  | ☺ |  | Ahead |
|  | Maintain LINK’s IT systems to enable efficient network communications. |  | IT support and training to LINK staff and day-to-day maintenance and backups | No IT impediment to network comms. | Ongoing | High | AFO |  | Suppliers (SCVO) |  | ☺ |  | Support from SCVO adequate and cost-effective. Good bi-annual support meeting w/ SCVO held on Oct 19th. |
|  |  |  | Interface between LINK office and IT suppliers |  | Ongoing | Low | AFO |  | Suppliers |  | ☺ |  | Ongoing |
|  |  |  | IT planning and improvement (incl project mgmt and implementations) | IT systems sufficient and cost-effective | Ongoing | Med | AFO |  | Suppliers |  | ☺ |  | IT upgrade plan for 2010 agreed w/ SCVO, and budgeted for in 2010-11 budget. |
|  | Finish revamp of LINK website and maintain. |  | New website due for completion April. Content to be transferred across during Q1 (AISO, DO, PAO). Updated generally by AISO and PAO |  | ongoign | med | AISO |  | DO, PAO |  | ☺ |  | Transfer happened Nov - thanks to PAO for transferring bulk of files. Staff training in Jan for keeping it updated. |
|  | Maintain Meeting room in Perth office. |  | Meeting room is free resource for members and TFs, available to other bodies for a fee. Staff maintain diary, supplies, clean, set up as needed. Externals invoiced. |  | ongoing | low | AISO, AFO |  | Perth staff |  | ☺ |  | Bookings for and maintenance of Meeting Room co-ordinated by AIO and other staff. |
|  |  |  | Create meeting space and encourage drop-in use of Edinburgh office. |  |  |  | PO, PAO |  |  |  | ☺ |  | Drop-in usage continues. |
|  | LINK outputs and reports are archived. |  | Master copies LINK’s reports kept & sent to Scottish and British national libraries. All LINK outputs routinely forwarded on production to SNH, SEPA, ScGovt, CoSLA, SPICe & others as relevant. |  | ongoing | low | AISO AISO / Parly staff |  |  |  | ☺ |  | On-going on a weekly basis to SNH, SG and monthly to others. |
|  | Maintain LINK’s database & lists to ensure info in-date and members receive all relevant |  | AFO & AISO coordinate review of needs 2009. AISO & PAO share responsibility for upkeep. All staff contribute where possible. TFCs/Reps regularly asked for changes. |  |  |  | AFO, AISO, PAO |  | Staff, TFCs |  | ☺ |  | Database improvements working well. New AISO bringing focus on data ownership. |
| TF example: | Working within operating plan, each TF elects Convenor and Depute to share TF leadership, planning and reporting to LINK. |  | TF reports quarterly for Reps, Funders, op plan and KPIs. TF presence and prep (evaluation, plans, spend) at 2 of 4 meetings pa. Outputs to meet standards (styles, operating principles) . |  |  |  | TFCs |  | Deputes Reps |  |  |  |  |
| STRATEGIC OBJECTIVE 3: AN EFFECTIVE, EFFICIENT, ACCOUNTABLE NETWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual Objective | Tasks |  | Action needed | Indicator | Timescale | Scale | Respons- ibillity |  |  | Support | Status |  | Comments / Progress |
| 3.2 Ensure LINK's activities are adequately resourced from a diverse range of sources | Identify the network's funding needs in advance of each financial year, maintaining leverage to range of funders. Ensure fundraising capacity is in place. Generate subscription income from member bodies to maintain autonomy. |  | FSG meets to consider future year’s funding need each autumn, towards new grant bids. AFO to confirm band threshold annually. AFO supports FSG in calculating subs rate to keep on track to agreed % goal and recommends to Board. | Budgetted subs income received within time period; | Q3/4 | med | CO/AFO Treasurer, AFO |  |  | Funding sub-grou | ☺ |  | Proposals from FSG for 2010-11 subs to be considered by Board on Jan 21st. |
|  |  |  | Members advised of following year's rate and asked for comment to resolve issues before AGM. Dialogue offered for members with issues. |  | Q1/2 | low | AFO |  |  | CO, Treasurer, | ☺ |  | Ongoing communication w/ members who have payment issues for 2009-10 |
|  |  |  | AFO generates invoices after AGM & manages prompt payments. | No bad debt by year-end | Q3 | low | AFO |  |  |  |  |  | One outstanding issue (FoLL) to be resolved for 2009-10 |
|  | Generate core grants from SNH, SG, EFF and administer grant internally. |  | DO submits core grant applications (1 per year, timing varies). DO reports six-monthly and annually to funders. DO ensures core grant conditions understood internally. Project managers meet grant conditions. | Grantors continue to core fund |  | med | DO, |  |  | CO, IO, AFO, FSG, PO |  |  | £62k confirmed for 2010/11. New apps to SNH needed for further years. Negotiations afoot on outputs and outcomes and SNH will ‘review’ LINK winter/Spring 2010. EFF re-application due 2010 for years ahead. |
|  |  |  | AFO submits quarterly claims (SNH, SG). | Grants received | Q1-4 |  | AFO |  |  |  | ☺ |  | On track |
|  |  |  | DO arranges six-monthly meetings with SNH (involving CO, PO usually and 1 with Chair). |  | Q2,4 | low | DO |  |  | PO, CO, Chair | ☺ |  | Met SNH Nov to discuss outputs/outcomes for 2010-11 – want this aligned to SNH new objectives. New annual liaison meeting with SG grant contact held Nov with DO and PO, went well. |
|  |  |  | PO quarterly meeting with SNH grant contact. |  | Q1-4 | low | PO |  |  |  | ☺ |  | First 2010 meeting to be arranged. |
|  |  |  | DO arranges for Trustees to meet core funders as needed. |  | Ad hoc | low | DO |  |  | Trustees | ☺ |  |  |
|  | Generate income for established projects. |  | SEW sponsorship approaches made late April. Congress sponsorship approaches made May. | Funding repeats/ New funders in. | Q2/3 | low | DO |  |  | PO, CO, Treasurer | ☺ |  | Success in getting HS grant of £5k for 2010 and support of £5k for further 3 years. No other funding achieved. |
|  |  |  | Reporting on SEW, Congress and other projects by relevant staff/project managers. |  | Q1 and ad hoc | low | PO, DO Id’ed leads |  |  |  |  |  | Congress report outstanding, will do asap. |
|  |  |  | Approaches to Lottery, charitable trusts, councils for other projects made as openings are seen |  | Ad hoc | low | DO |  |  | CO, AFO | ☺ |  | Bid to P&K for Biodiversity conference £1k successful. |
| 3.3 Ensure LINK evaluates key activities and the network applies learning to improve corporate performance | Encourage TFs and project steering group to evaluate via AARs and peer review / Board interview at Network meetings, and evaluative reporting via pro-formas quarterly. Assess value over 3 years of LINK contributions. Apply lessons to planning of network activity. | TFs to evaluate progress against strategic objectives at networking meetings once x year |  |  | Q1,2 | low |  | TFCs |  | TF members |  |  | Nov 09 discussions agreed 6-monthly review of strategic issues, new opportunities, changes in context, and consequent requirement for changes of direction or emphases for LINK. |
|  |  | After action reviews for projects; staff member or project manager to arrange and report to board and networking meetings |  |  | Q4,1 | low |  | Rel Staff, Project managers |  | St groups |  |  | Due spring 2010 |
|  |  | Information for Operating plan upkeep and KPIs to be sought and collated, log maintained |  |  | Ongoing | med |  | CO |  | DO, AISO, designated leads. |  | ☺ | Staff on track with this |
|  |  | Stakeholder evaluation undertaken annually facilitated by AISO. Communicate views to SGovt. |  |  | Q2 | med |  | AISO Chair |  | Delegates to forums |  |  | See earlier entry – staff propose dropping this, esp as we are not using the information we collect to look for changes in practice. |
|  |  | Carry out survey with opinion formers and decision makers in Spring 2009. (to repeat early 2012). Survey members in parallel during 2009 (to repeat during 2010 and 2011). Consider survey feedback with Reps, TFs and Board at network meetings. Determine how to change practice. |  |  |  |  |  | CO CO Chair |  | Board/PO Board/staff All actors |  | ☺ | Discussed. Reluctance to seek ext feedback beyond than current three-yearly strategic review. We know we are effective, can point to anecdotal and recorded evidence. So next external survey 2011/12 - in strategic review. Meantime, for SNH reporting, internal surveys likely to be needed last quarter of 2010/11. We do consider feedback from external or internal members at Board or Networking level. |