## StrObv1
LINK BOARD 27 October 2016 Operational Plan 2016-2019 Report Paper 3.1
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Advocating for a sustainable Scotland | Scottish policy and its implement-ation are improved by expertise and evidence from the LINK network | LINK sharpens its focus to prioritise collaborative work on a smaller number of resourceable priorities, to have greater impact and influence. | Chair, MBs, Groups, CO, AO, MPAOs, SEO | Our priorities are selected to target relevant Government priorities such as jobs, fairness, wellbeing. KPIs 1.5, 1.9, 1.10. Baseline April 2016: Inputs consistently good, take up patchy | Inputs very good, take up improving: Election, referendum, recess over period. Strong effort to build relationships since. Some success (eg 3 ministers met, contact with MSPs). Groups report: Rebuffed by CabSecEconomy; Marine invited to ECCLR cttee and asks for commitments to further MPAs, Inshore Fisheries Bill and marine planning are in Govt's programme. Land sees good references to our manifesto asks, meetings with CabSecs, senior civil servants and Brexit Min (ahead) a credit to the work of the advocacy team; great start to relaunched Spec Champs (over 50 MSPs) and good relations with committees. Planning reports a mixed picture, our advocacy mesage that planning should be central to wider governance/policy making was picked up and our call for better integration of Planning Fmwk, LU strategy and national marine plan also supported in principle, may carry forward to White Paper; however Equal Rights Appeal specifically rejected. Governanceconfirms manifesto asks picked up, good contacts across parties ahead of elections, commitment to biodiversity by SNP and 'ask' about ending environmental poverty picked up by media. Social justice work aiming to link environment to Fairer Scotland action plan was not successful, though interest in Environmental Poverty Act by party spokespeople.
|  | LINK strengthens its advocacy around those priorities, developing positive, solutions-focused approaches, communicating clearly about what we stand for. | All players | Sustainable approaches, for Scotland and beyond, have more traction with decision makers. KPIs 1.1 to 1.6, 1.7, 1.8, Baseline April 16: Good- improving | Good, steadily improving: There is greater clarity about our strategic messaging among our groups and subgroups. More of these groups requesting help of AO with advocacy strategies and working with decision makers. Planning article in FoS offered solutions: Chief Planner has commented positively. Economics' September briefing on economy having positive feedback (Con, Lab). Motion in support of our 'Living with Seas' report was tabled. Post-Brexit, our advocacy for LU strategy to be applied strategically as a solution to some current challenges gaining some traction. Despite early positive signs our advocacy on environment in relation to Fairer Scotland is not reflected in the Govt's published plan. Relations are getting more positive on wildlife crime. Relaunched Specs Champs has 50+ MSPs since May showing popularity of approach.
|  | We work with Government and other key decision-makers (through strategic dialogue, stakeholder forums, evidence, submissions, events) to help achieve sustainable development, collaborating closely as an effective way to exert influence; | Chair, trustees, Groups, Sub-Groups, MBs, delegates, staff: AO, CO, DO, MPAOs, SEO | LINK keeps Govt to account on obligations, and public clamour for change grows. KPIs 1.7, 1.8,1.11 Basline April 16: Good constructive relations. | Good and improving: Good constructive relations continue as meetings with Ministers, senior officials, MSPs, SPADs indicate. Many LINK submissions, briefings and pres work over period. Some traction for join-up on planning (see above) of government's strategies and policies. LINK's recent proposal for a National Enviornmental Network (to be developed) aims at strategic level. However, Fergus Ewing so far unsympathetic to us on fisheries and agriculture issues, and still chasing dialogue with other portfolios. Met SG official for Fairer Scotland programme. Met with Greens.
|  | We will improve our local, national and international linkages to broaden the shared voice | Chair, trustees, MBs, Groups, staff mainly AO, CO, local links lead, MPAOs, SEO | Delegates on forums which are 'gaps'. Involved in obvious stakeholder groups. LOCAL matchmaking dbase well used. KPIs 1.6, 1,11. Baseline April 16: Improving | Good: LINK engaged in EEB 2016 conference and is to co-host 2017 conference with EEB in Scotland. LINK supported various motions for IUCN Congress 2016. Proactive with colleagues since June vote on Brexit (ongoing). Engaging with ELUK and Rep of Ireland network at various levels. Maintaining LINK Local database (40-50 groups have joined). LINK would benefit from a stronger means of engaging with the IUCN agenda perhaps esp. in light of Brexit.
|  | We will advocate robustly for the environment in the public interest. | Chair, trustees, Groups, Sub-Groups, MBs, delegates, staff: AO, CO, DO, MPAOs, SEO | LINK keeps Govt to account on obligations, and public clamour for change grows. KPIs 1.7, 1.8,1.11. Baseline April 16: Good - room for improvement | Very Good: Post-election, there is no internal sense that LINK is not being sufficiently robust. May be indications that earlier strength of advocacy on wildlife crime is bearing fruit. Some rumblings now ongoing about environmental places on the Scottish (Brexit) Standing Council. Planning's ERA campaign so far rebuffed and we still have our problems on biodiversity, land use. Looking ahead on agriculture, bio etc, the job is more one of mobilising wider support to convince decision makers of the need for a change in direction.

## KPI for 1.1 - 1.11
Outcome KPIs:
1.1 Extent to which LINK asks, messages and language are known to be used in parliamentary debate, FMQs, policy papers, and are reflected in the manifestos of the main political parties. Baseline at 2015-16 - Poor, Improving some areas
1.2 Level of M(S)P support for LINK network messages e.g. numbers of M(S)Ps attending LINK events; expressing commitment to environmental issues; Issues raised by LINK at meetings with decision-makers and opinion-formers taken forward by policy makers. Baseline is good at 2015-16
1.3 Level of Scottish Parliament scrutiny of delivery of environmental commitments e.g. delivery against SD Goals, targets in National Performance Framework, environmental principles informing decisions on development in Scotland, proposals in LINK’s ‘Governance Matters’ are met. Baseline - Poor, Improving some areas
1.4 Extent of Government cross-compliance across departments e.g. strategies and delivery are joined up (bio, land use, climate, economics, etc). Baseline: environmental measures in CAP/SRDP at 2015 are ‘not so good’
1.5 Extent to which Members and Groups in the network actively contribute to development of effective environmental policy.
Target: 66% of members participate in cycle of network meetings, 80% are involved in at least one Group. Baseline Good.
1.6 Connect more with other organisations and alliances. Target: eg other organisations are calling for similar/same things.
Output KPIs:
1.7 Size and mix of audiences at LINK events (from among decision-makers, opinion formers and wider civic Scotland)
1.8 Level and frequency of LINK (Board, Groups, Staff) access to decision-makers including MSPs/MPs/MEPs, Ministers, senior government officials and business leaders E.g. regular meetings with Environment Minister continue; LINK is involved in relevant forums. Target: at least 25 exchanges per year reflecting breadth of LINK agenda. Baseline Good/Very good
1.9 Number of collective position statements (including briefings, publications) that are published by LINK to decision-makers and civic society on key priorities reflecting the range and diversity of interests across the LINK network. Target: At least 15 per year, drawn from the Groups, in which at least 5 members are actively involved (per Group) and which meet at least 4 times a year. Baseline Very good
1.10 LINK Groups to plan their communications to various audiences highlighting the solutions focus and being clear about what they stand for.
1.11 Group plans to identify all relevant allies who share some of our agenda and the steps for joint work to increase impact. Eg., connect more with other organisations and alliances, look for opportunities to bring an environmental perspective to other agendas such as social justice.
Target: Groups and Subgroups identify annually appropriate linkages and follow these through. Baseline Room for improvement
SNH6: Provide a gateway for Government and RAFE partners among others to enable them to engage with the voluntary environment sector efficiently through LINK as the Intermediary.
SNH7: Provide evidence based feedback about how Scotland’s environmental objectives and obligations are faring through the various delivery mechanisms, via Ministerial and other meetings with officials, briefings and other LINK publications

## Str Obv 2
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Being a strong voice for Scotland's environment | The voluntary environmental community's contributions to evidence-based policy are stronger | Robust prioritisation, post-horizon scanning, is achieved, clear on member leads and support, so that LINK can do less, better | Chair, Trustees, MBs, Groups, CO, AO, AOA, DO, MPAOs, SEO | LINK work programme delivers powerful advocacy around fewer key issues/campaigns. KPIs 2.3, 2.5, 2.9, Baseline April 16: Good | Good, Progress steady. There has been no requirement to repriotisise since Nov 15. May network meeting stressed importance of relationships cross-portfolios, parties and with new MSPs. UK EU vote brought Brexit which all agreed is (a new and so far additional) priority.
|  | Policy messages are integrated both between LINK Groups and with member bodies' own work, to increase impact and resonate with national social and economic priorities. | Group Conveners & identified communicators; MB Reps on Groups, Main Reps. | Member organisations' efforts are aligned, to achieve the above. Baseline April 16: Good though hard to assess alignment with MPs' work | Good progress and improving. Working well across our land-focussed groupings. Level of member commitment and engagement would indicate LINK work underpins members' own goals. Good comms between Groups through both the staff pariticpation and degree of member overlap. Social justice effort drew on many members and groups.
|  | Diversity of view is always explored, consensus accurately represented, and different approaches of members used to good effect, in developing positions | Groups, Conveners; Subgroups; MBs, Staff, Delegates | Positions, including differentiation, confidently expressed externally, so that shared 'asks' are clear, KPIs 2.3, 2.10, 3.5, 3.6 Baseline April 16 Good-improving | Good, improvement continues No issues raised. Marine have addressed differences on fisheries, with success and identified aquaculture (at least in MPAs) is needing more discussion. Economics is working on a Natural Capital consensus statement. Land and Economics see a need to talk about concept of public funds for public goods. Governance feel the network is very live to breadth of diversity and where this is more likely.
|  | Internal agreed positions on our priorities are swiftly communicated across the network (among Groups Subgroups and Members) | Group Conveners & identified communicators between Groups & Subgroups; all MBs on Groups & Subgroups; Main Reps. Staff for bulletin & website. | Network and its members are aware of internal positioning, KPIs 3.7. Baseline April 16: Comms of outputs good. | Good: Communication of outputs is good via websites, bulletin, social media. Staff and members have been identifying some issues which Groups may need to collaborate over. Extent to which outputs are known by those in LINK other than the signatories (ie others who should know) is unclear, but no problems identified in this period.
|  | Connections are established with other civic sectors and coalitions, actively looking for opportunities to bring an envionmental perspective to issues of shared interest | Board, Groups/Conveners. Staff: AO, MPAOs, SEO mainly | Common ground developed with other civic sectors and coalitions and increases the size of the voice, for positive, timely action KPIs 1.11, 2.1 Baseline April 16 : Good | Good and improving: In this respect most groups have been proactive. Congress 2016 will specifically explore linkages with other sectors.
|  | Groups and relevant Subgroups develop their advocacy strategies at the outset, robust for the environment in the public interest. | Groups/Conveners, AO, MPAOs, SEO, CO and Board. | Advocacy strategies are monitored and adjusted to be fit for purpose and changing circumstances KPIs 2.7, 3.6 Baseline April 16 Good, in hand, | Good and improving: Development of advocacy strategies gradually becoming routine.
|  | LINK consistently communicates key messages through website, social and other media to be relevant and resonate. | AO, DO, AOA, FOM, MPAOs, SEO, Interns | LINK website reflects current strategic priorities and positions in a way that engages our audiences. KPIs 1.10, 2.5.: Baseline April 16: Good and improving | Good and improving, still.
|  | Making best use of Hon Fells | Board, Groups, staff involved in facilitating the work. | How are Hon Offs involved in supporting Groups / LINK's work. Baseline April 16: Improving | Good -Improving. Fellows are aware that they can engage; 4 or 5 have been involved over the period. Allare invited to network events. Newfellows were brought on specifically for their expertise and are engaging.
|  | Network skills in advocacy (comms, negotiation) are explicitly considered and provisioned appropriately when developing our advocacy strategies | Groups, Subgroups, AO, MPAOs, SEO, CO | advocacy strategies reference skills? Convenors report back on it? KPIs, 2.4, 3.6, Baseline April 16: Variable | Improving: Summer training extremely well-attended and valued. Two of our Groups or Subgroups are seeking help in developing advocacy strategies. Some groups feel they score well. Others have had limited negotiating opportunities in period. However, some groups report not having developed advocacy strategies, yet.

## KPI for 2.1 - 2.10
Outcome KPIs:
2.1 LINK is contributing to relevant stakeholder groups/discussions to bring the environmental perspective. Baseline Good, but we need to extend our reach
2.2 Level of participation at and feedback from Group meetings, internal workshops and trainings arranged by LINK for members (on current issues, or skills needs). Target: 2 workshops or trainings arranged by staff per annum. (SNH target also) Baseline Good
2.3 Extent to which Groups influence direction of policy through good tactical planning. Targets: Groups are alive to the diversity of views within the network on the given issues. Advocacy strategies build on our strength in diversity, address practical issues of giving robust criticism (i.e. planning for the fallout), members and stakeholders value our ability to promote mature debate, inform policies and represent different voices.
2.4 Level of improvement in negotiating skills, based on Groups identifying their skills needs and these being addressed. Baseline: 3/13 TFs at 2015 felt things were good enough – so there is scope for improvement
2.5 LINK’s ability to add value as a collective voice. Baseline very good.
2.6 LINK Elected Trustee positions are mostly filled from within the network, annually. Baseline 8 of 9 at November 2015.
Output KPIs:
2.7 Number of networking events/opportunities and members participating in them (e.g. information exchange, policy workshops and training, negotiating skills). Target: 6 meetings/events; 2 workshops/trainings annually.
2.8 Number of opportunities afforded to meet and learn from other members. Target: minimum 8 (to include network level event and Groups and Subgroups in which hopefully every member is engaging at a minimum)
2.9 Identifying clear and resource-able network priorities with members from among the identified collective concerns. Target: that each annual planning meeting will identify these, and also agree areas which members will drop in order to resource the fresh priorities.
2.10 Number of collective position statements (including briefings, publications) that are published by LINK to decision-makers and civic society on key priorities reflecting the range and diversity of interests across the LINK network. Target: At least 15 per year, drawn from 5 Groups in which at least 5 members are actively involved (in each) and which meet at least 4 times a year
SNH1: Maintain a range of active Groups and Subgroups to be a forum for discussion and a platform for joint action, in which management of nature/environment forms a key element.
SNH2: Provide advocacy advice and coordinating support to Groups; horizon scanning of the broader socio-economic-environmental-political contexts at national and international levels; twice yearly political strategy reports for the Board and Network meetings; advice on advocacy strategy as Groups request it; ensuring regular reporting of progress on all topic areas; annual evaluation of Group and Subgroup activity to share learning across the network.
SNH3: Organise at least one training event (e.g. advocacy, media skills) for members annually, to improve members’ effectiveness in these areas
SNH4: Organise liaison meetings at strategic level with SNH and other SEARS/ENFOR partners (e.g. SEPA, FCS, National Parks, divisions within SG) a yearly basis; and with other key stakeholders in the policy community (e.g. land managers, faith groups, business interests, civic groups, academics, professions, trade unions, political parties, media, funding bodies) to establish relationships and build common cause for sustainability goals.
SNH8: Provide information to members through LINK’s membership and engagement with UK, EU and global networks to assist member bodies prepare for and react to changes in policy affecting Scotland’s environment.

## Str Obv 3
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Operating as an effective, efficient and accountable network | Operational capacity and processes meet network needs and goals | Annual planning process brings the network together, prioritises annual work programme to achieve strategic aims, resourcable and well led and focussed, which is reviewed at the two annual network meetings. | Chair, Trustees, Group Conveners, Subgroups, MBs, staff: CO, DO, AO, MPAOs, SEO | Annual work programme agreed informing agreed operational plan. KPIs 3.4, 3.5,3.6, 3.7, 3.9, 3.11, 3.13. Baseline April 16: Good so far, new process | Good, room for improvement: Some Groups still see need for Board to help LINK to drop x, y in order to deliver better on a, b. There is an increasing pull on Advocacy Officer time from Groups and Subgroups. Project staff funding uncertainty will exacerbate the sense of capacity being limited, ahead. 2016's strategic planning discussion needs to prioritise even more than in 2015, if we are to work within available capacity of members and of staff.
|  | Intelligent horizon scanning ensures connection of LINK's annual priorities to relevant social and economic themes | Chair, AO, CO, MBs, Conveners, Governance Group | KPIs 3.13, also 1.6, 1.11, Baseline April 16: Good to Very Good | Good to Very good. VG horizon scanning; are resource issues for LINK in following through sometimes, where member capacity is limited (eg economics, LINKLocal, EEB, how environment contributes to social justice).
|  | Group processes of agreeing priorities, integration, leadership (C & VC) are followed. Networking meetings and Board provide peer review. | Group Deputes, CO, DO | Plans reflect capacity, resources, strengths, integration and strategic goals, KPIs 3.3, 3.6, 3.7, 3.8,3.9. Baseline April 16: Good so far | Good, issues remain. Groups and Subgroups know what they want to do, are assessing capacity, but find it very hard to drop things that are not the agreed priorities. Continues to be much reliance on a few key individuals in many (not all) groups and subgroups. Leadership is generally not a competitive issue. Network meetings have worked well in providing peer review.
|  | Groups communicate enough with other Groups, Subgroups and LINK centrally | Conveners, identified communicators, Subgroup Leaders; staff for website, emails, bulletin | Work plans and Members are clear about connection between Groups and Subgroups. KPIs 3.7. Baseline April 16: Good? | May be improving. Relies on staff and those member reps who are involved in more than 1 area, for effective communications. This is up for review at strategic planning.
|  | Forward planning identifies relevant allies, audiences, forums and action |  | Plans supported by clear advocacy strategies. KPIs 3.11, Baseline April 16: Good. | Good. There are capacity issues in building relations with allies.
|  | Staff capacity to support Groups is sufficient. | Chair, AO, CO (and other allocated staff) and Network review discussions. | Staff work plans are clear about support to be provided to Work Programme. KPIs 3.10, 3.14. Baseline April 16: Good currently | Good - problems ahead! 6 Groups being serviced currently by staff as promised. Uncertainties over 3 project staff from 2017 and Intern for another work area, which may significantly reduce support to, and therefore affect the impact of, 3 Groups. Staff workload is consistently busy. AO now noticing increased pressure on time.
|  | Core events (Congress, SEW) support strategic priorities. | Groups, Trustees, DO, AO, AOA | Events address priorities, KPIs 2.9, 3.3, 3.9. Basleine April 16: Good | Good: Congress addressing Brexit and links with social and economic agendas. SEW 2017 - ambitious programme developing, making links with other sectors.
|  | Groups identify differences in organisations' views which could affect consensus (where that is a goal) and bottom out; problems are flagged to the centre for advice | Conveners, Deputes, Advocacy Staff, CO & Board | Differences in view which may matter are properly considered KPIs 3.5, 3.6, 3.7. Baseline April 16: Good | Good: Economics addressing Natural Capital. Marine looking at aquaculture and have addressed fisheries. Governance negotiated manifestos development, is live to diversity. No issues in Planning. There are groupings where non-engagement by what seem to be 'obvious members' is flagged as an issue, including wildlife crime (no longer has NTS, SWT involved), economics (WWFS addresses economics issues, but independently). Marine is working to re-engage RZSS after its staffing changes. Land is on top of things. Social justice messages harmonised, building on what is already developed by groups and subgroups.
|  | Members are given scope to present to network and talk with trustees about engagement and prospects | Chair and CO | Members know each others plans. Board understands membership KPIs 3.2. 3.4, 3.8, 3.9 3.11, 3.12, 3.13. Baseline April 16: Good | Good: Yes, at network meetings. Bulletins offer scope to members. Contact meetings continue to be offered via the Bulletin. In this respect, note the two unexpected withdrawals from LINK (Sustrans, SOC), however.
|  | Relevant audiences identified, allies with which to connect, forums requiring environmental voice | Chair and CO, Conveners for Group planning, Leaders for Subgroup planning, advocacy staff | .Number and nature of relevant audiences, allies and forums identified? KPIs 1.6, 1.10, 1.11, 2.1,. Baseline April 16: Good | Good: Process is being followed
|  | Evaluation is done for and by Board and Network meetings, informs on progress and pace, and plans are adjusted in the light of learning | Group Deputes, CO, DO, Trustees, Conveners | Evaluation complete, KPIs 3.11; Baseline April 16: Good | Good: Process is being pursued. Extent to which lesson learned and plans adjusted difficult for staff to know - Strategic planning to explore.
|  | Liaison meetings | Chair of meeting, staff organiser, MBs attending | Meetings are well prepared for and used strategically. KPI 1.8, 2.4 Baseline april 16: good | Good: Ministers, MSPs, Agencies, and other meetings via Groups held. All have been prepared for, are coherent.
|  | National organisations eligible for membership want to be part of the network and member bodies want to stay in LINK | Board (FSG) & staff monitor engagement levels & are proactive | 90% of members engaged in Work Programme, KPIs 3.1, 3.12 Baseline April 16: Good. | Good: Two departures. Two fresh applications, a further application may be pending. Have not seen JMT responding to overtures to rejoin, yet.
|  | Board ensures skills, diversity and CPD opportunities | Trustees (Subgroup), MBs, CO facilitates | Board membership is appropriate. KPIs 2.6, 3.4, 3.12. Baseline April 16: Good | Good: Skills register updated, succession planning ongoing, Chair reported on three-yearly meetings with trustees in 2015; opportunity for trustee 'trainings' has been flagged.
|  | New member organisations, fresh Reps, new Trustees and incoming Staff will be given very good inductions, with follow-up in the first eighteen months | CO, DO, AO, and other staff and trustees/deputes as needed | Members understand how LINK operates and how to engage. KPI 3.4 Baseline April 16: Room for improvement | Improving: Ongoing for members, new staff, new conveners/leaders.
|  | LINK policies on employment follow good practice and ESG plays active role in monitoring | Board, CO, FOM | Confident, supported staff supports delivery of strategy, KPI 3.14 Baseline April 16: Good | Good: Handbook updated twice recently. ESG reviewed salaries and terms and conditions with awards due from October.
|  | LINK policies for staff, Groups and delegates are followed | Board, CO, FOM, anyone organising events | Ops carried out in line with SD values, KPIs 3.4 Baseline April 16: Good-ish | Good: These are followed and esp. where staff are involved. No problems identified.
|  | LINK funding strategy looks 5 years ahead | Board (FSG), CO, DO, FOM | LINK's stability for 3 years ahead ensured, KPIs 3.10. Baseline april 16: Good, scope for improvement | Good: Fundraising is tougher. Longer term scenario revised, FSG delegated to advise.
|  | Funding is a blend of membership (at least 60% of Essential Costs) and external, with public sector meeting <25% total income | DO, CO, FOM. Board FSG | Independence of voice & resourceability of strategy ensured, KPIs 3.10, 3.14 Baseline at April 16: M'ship accounted for 57% of ES. | Amber warning: M'ship accounts for a bit less than 60% Essential Costs owing to loss of Sustrans mainly. Public sector future remains uncertain. The trusts/foundations element of our funding is definitely diminishing. Corporate sponsorship is challenging given member preferences around this.
|  | Active Board meets at least quarterly to assess progress | Trustees, CO, DO, AO, FOM | Delivery of strategy is monitored KPI many relate Baseline April 16: Good | Good. Meets regularly, is quorate. One expression of interest in board membership from 2017 received so far.
|  | LINK's administrative functions are kept under review | CO, FOM, AOA, DO | Admin supports strategy and effective running of organisation, KPIs 3.14 Baseline April 16: Good | Good: 2015 review of staffing functions made various adjustments which have been positive. the 2015 provision to increase core staff complement from 4 FTE to 4.5 FTE is challenged by funding situation. FSG and ESG will develop a contingency plan from early 2017.

## KPI for 3.1 - 3.14
Outcome KPIs:
3.1 Number of citizen-led, national level eNGOs that are LINK members (i.e. leaving/joining/sustaining membership annually)
3.2 Extent to which members are aware of LINK priorities and opportunities to engage with these. Baseline: members are offered 1:1 meeting with a trustee, annually.
3.3 Process for setting and agreeing priorities is implemented and reviewed. Targets: There are no more than 5-6 priority themes (Groups) at a time through which all Subgroups operate.
3.4 New Members, Reps, Trustees, Staff receive very good induction and follow-up within eighteen months – this informs member on how /where they can engage. Baseline: very good inductions at 2015; more time needed in follow-up
3.5 Extent to which the network is live to the diversity of member interests and views. Target: Strategic Planning, Groups, and Board, encourage full membership engagement in policy work all members to be aware of the issues being addressed and the direction of any likely consensus. Baseline: Structures allow members’ views to come through (eg Board’s 1-1 contact with members, Groups and Subgroups in which members can engage)
3.6 Groups are explicit about strengths and diversity, and reflect these in their plans and tactics. Baseline at 2015 Poor
3.7 Extent to which LINK messages are harmonised, avoiding contradiction or duplication, collaborating when needed. Targets: Groups are consistently represented at Network meetings. Groups pursue strategic LINK priorities. Group-to-Group communications flag intents and integration needs.
3.8. Extent to which Subgroups and Groups are aware of the spread of members in the network and are content that all relevant members are participating and feel their goals are met. Baseline: Very good under TF structure at 2015. (May need to assess this annually with members)
3.9 Annual network Work Programme reflects considered discussion and priorities and engages at least 75% of members in its delivery. Baseline: Very good under TF structure
3.10 There is a breadth and blend of financial support for LINK from a range of sources to sustain LINK’s independence and maintain our right and responsibility to be a strong voice for the environment.
Targets:
· Membership funding underpins 60% of essential services
· Government/public sector funding for 2015/16 represents no more than 25% of total income
· Business support for LINK (as event/initiative sponsors or as Business Supporters) represents 7% of total LINK income by 2016/17
Also:
2.6 LINK Elected Trustee positions are mainly filled from within the network annually.
Output KPIs:
3.11 An annual Work Programme of the network’s intended work is prepared with Member, Group, Subgroup and Board input, and is subject to twice yearly review and evaluation. Review should include the extent to which the plans are resourced and members’ have made commitment to implementing them.
3.12 There is proactive engagement by 90% of members in some area of LINK policy or governance annually. Baseline: 90% at 2015
3.13 Annual strategic planning process gives members a platform to present on their directions, allows the network to collectively sign off on priorities for joint work ahead, with up-to-date intelligence about goals and contexts, and identifies leads and those responsible for integration. Baseline: Check at May 2016
3.14 Board (with FSG and ESG) reviews whether the organisation is stretched, working at (or over) capacity – ie whether the money, time, personnel, membership, skills and knowledge available are fit for the priorities. Includes at a minimum: staff support to every Group for arranging, attending and minuting up to 4 meetings per year; fundraising time is available for priorities; processes and structures encourage collective work under the LINK umbrella rather than outside that umbrella. Baseline: tbc end 2016.
SNH5: Organising 3 network meetings per year at which stewardship of Scotland’s environment is discussed in the round by LINK members and Groups, plans are adjusted as events develop, further workshops are organised as needed, lessons are shared and new opportunities explored.