This Work Programme sits below LINK’s Strategy for 2016-20 and its Operational Plan.

The Strategy sets out in broad terms what the Network aims to do.

The Operational Plan sets out what is required to achieve our strategic objectives over 3 years; identifies the responsible players (members, groups, Board, staff); the relevant KPIs and baseline targets, and, via feedback from key players in the network, assesses strategic progress for the Board’s overview and for Members’ information, every 6 months.

This (annual) Work Programme outlines all planned activities of each LINK group and subgroup, as well as plans for broader LINK meetings, workshops, receptions, initiatives and liaison.

It is gathered in a single document so that all involved in LINK can see intentions of the network and help to identify where integration between work areas is needed, to strengthen impact, prevent duplication and contradiction.

The intention is that we report on progress, to the Board and to the Network, every 6 months in May and November.

Besides 5 strategic Group areas, and numerous Subgroups, there are 2 Forums operating more loosely as a valuable means of information sharing and capacity building for their members.

And the programme of core work is included in the final pages.

KEY to ACRONYMS

| MBs | Member Bodies (of LINK) |  | Strategic Groups |  |
| --- | --- | --- | --- | --- |
| Reps | The main Representatives appointed to LINK by the member organizations |  |  | Economics Group |
| GC/GVC | Conveners and Vice Conveners of the Groups |  |  | Governance Group |
| SGL/SGLD/FL/FD | Leaders and Deputes of the Subgroups and Forums |  |  | Land Group |
| CO | Chief Officer (Deborah Long) |  |  | Marine Group |
| DO | Development Officer (Alice Walsh) |  |  | Planning Group |
| AM | Advocacy Manager (Daphne Vlastari) until July. Vhairi Tollan from September. |  |  | Social Justice is a cross cutting theme, rather than a Group. |
| FOM | Finance & Office Manager (Karen Paterson) |  | Subgroups |  |
| AOA | Advocacy Office Administrator (Lisa Webb) |  |  | Aquaculture Subgroup (part of Marine Group) |
| AO | Advocacy Officer (Dilraj Watson) |  |  | Brexit Subgroup (part of Governance Group) |
| MPEOs | Marine Policy and Engagement Officer (Esther Brooker) |  |  | FFSN Campaign (part of Governance Group) |
| SEO | Sustainable Economics Officer (Phoebe Cochrane) |  |  | Deer Subgroup |
| FFSN CO | Fight for Scotland’s Nature Campaign Officer (Miriam Ross) |  |  | Food and Farming Subgroup |
| SCC | Species Champions Coordinator (Calum Langdale) until October. |  |  | Hilltracks Subgroup |
| HF | LINK Honorary Fellow |  |  | Landscape Subgroup |
| StrG | Steering Group (Projects, Congress etc) |  |  | Land reform, land use Subgroup. |
|  |  |  |  | Legal Strategy Subgroup (Part of Governance Group) |
|  |  |  |  | Wildlife Subgroup incorporating Species Champions project, and National Ecological Network. |
| PSR | Political Strategy Report |  |  | Woodlands Subgroup |
| OS | Organisational Supporters |  |  | Wildlife Crime Subgroup |
|  |  |  | Forums |  |
|  |  |  |  | Media Forum (not regularly meeting). |
|  |  |  |  | Scottish Environmental Fundraisers Forum (meets quarterly) |

| Current work area | Plans re: LINK objectives: improvement of national policy & implementation; improved capacity of network to contribute; effective network. | Specific tasks, targets, timings, advocacy strategy | Leader-ship and support | Staff roles/ Funding/ Fellows et al | Integration within LINK | Wider allies and liaison - Audiences | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Economics Group Vision: influence the current debate on economics in Scotland | The Circular Economy project is directed at creating new policy and legislation and ensuring implementation It will also significantly improve the capacity of the network to contribute in a policy area with which many member organisations are concerned but none have much capacity | CEFF project: Develop more detailed knowledge of and plans for our work in the three sectors: agriculture, plastics and carbon. Assessment of the strengths and weaknesses of the different policy measures which can promote circularity and their use in Scotland. Prepare a position on the content of an ambitious Scottish CE Bill with reduced material consumption as a target. Agree remit for an Advisory Group and invite membership Develop relationships with organisations outwith LINK to be allies in our advocacy Hold an event in parliament to raise awareness about the importance of a CE (June) Work with other LINKs on UK policy areas and consultations such as EPR, tax on plastic bottles with less than 30% recyclate, position paper on plastics. Engage with SG on their consultation on ‘re-use of other materials’ as in Programme for Government Investment for a Just Transition. Influence the design of the Scottish National Investment Bank to make sure it is aligned to a core purpose of a sustainable/low-carbon and equitable economy. Support advocacy for a statutory Just Transition Commission with sufficient powers and resources. National Performance Framework. Monitor use of NPF and seek to use it to advocate for LINK policies Contribute to Round Table and in other relevant forums in particular critiquing the primacy given to ‘sustainable economic growth’. Timetable There was a workshop at in December 2018 for LINK and externals to brainstorm priorities for shifting our economy towards circularity. There will be a concrete outcome to this event in the form of a shared position statement to be finalised by Spring 2019. Event in parliament to follow above plus MSP engagement (June) Consultation responses – exact timings not known Coalition building – on-going Policy background: Per project proposal to funder. Objectives: Our main ask is that economic activity in Scotland becomes more circular and that this results in reduced material consumption. Media dep. on hooks We need to influence SE and HIE so that business support is aligned to CE ambitions. Media may be useful for this. Advice will be sought from the AM. We are expecting the first material flow data for Scotland to be available in the early spring. This will be an opportunity for some media work. Also when UK data updated, ELUK opportunity. | GC Matthew Crighton (FoES) GVC Bruce Wilson (SWT) FoES, SWT, HWDT. Less regular attendance from RSPB, MCS, APRS, WWF. | SEO – LINK’s 3-day week dedicated post funded by Friends Provident Foundation. Also drawing on and linking to work carried out by others, in particular ZWS. Advice on advocacy will be sought from the Advocacy Manager as and when required. HF James Curran attends some meetings and is very available for advice via email. | Work on Plastics crosses over with Marine. Work on NPF overlaps with Governance. Consideration of powers regarding Circular Economy overlaps with Governance. The intention is that the CEFF project will have a focus/ campaign on a yet to be decided area of interest to LINK members. This is likely to have cross -over with another LINK Group. For example, if the focus was on better use of on-farm waste, it would be relevant to the Food & Farming subgroup. | Key Targets: SG and MSPs. Also account managers in HIE and SE, business associations, investors. There will be a need to brief Committees at opportune times depending on timings of White Papers/Bills. Likely to be opponents amongst some business quarters. Zero Waste Scotland is one of the key organisations of relevance to the CEFF project due its expertise contacts & networks it can access. Meetings have been constructive and they are willing to continue to engage with the project. SEPA also key. Efforts made to meet with the key individual on CE & we will continue to seek dialogue. SGovt is key as we hope to engage with them in their deliberations on what to do next re CE, after deposit return. A meeting was held with the key official & agreement to keep in touch. There is a loose grouping of Scottish based organisations interested in & campaigning on plastics. We have an agreement to meet every 6 months & share information in the interim. We have developed relationships with CRNS, which gives us links to grassroots enterprises working on re-use. RSA Scotland & SCDI have been allies in the past and we need to re-establish relationships. We are seeking broad support for our ask that CE initiatives should seek to reduce material consumption. In the coming months we will meet with reps of the Scottish Environmental Services Association & also seek meetings with SE, HIE, Scottish Remanufacturing Institute, Centre for Engineering and education development, & other bodies suggested to us. There is likely to be a SG stakeholder engagement on the CE by early 2019. We anticipate engagement. Working with ELUK on plastics position paper & will also work together on other UK issues, including consultation on Extended Producer Responsibility. Engaging with EEB groups on Waste and Eco-design. Currently trying to follow up interesting thread on eco-design. | Scottish National Investment Bank – Consultation response sent May 2019 and briefing for Stage 1 debate Sept 2019. Circular Economy for a Fairer Footprint – various outputs are on the website. There was a ‘Meeting’ in parliament hosted by Angus MacDonald in June which coincided with the launch of our paper calling for a strong CE Bill 37 organisations signed up to paper calling for a Strong CE Bill, forming the basis of our informal coalition. Including Project Heather, Oxfam, SMaSH, KSB, Soilutions, Ricardo Energy and Environment, Circular Edinburgh, IBioIC, EAUC Scotland, Wellbeing Economy Alliance, Remade Network, Green Alliance, CRNS. Two meeting were held with coalition members, discussed the content of the paper calling for a strong CE Bill, areas of expertise and interest, capacity to take part in a ‘campaign’, how to work together. Outcomes – coalition members spreading comms through social media, a google drive platform for sharing information, an agreement to work together. Meetings with MSPs (env spokespeople) and party researchers held (all were receptive of our asks) Meeting with CE civil servants – discussed timeline of CE consultation / bill; and what we would like to see in it. Meetings with Zero Waste Scotland – information sharing. Press releases put out for the launch of our ‘Call’ and for the first coalition meeting – both were picked up. Ahead: An event for LINK members plus wider coalition linked to the CE consultation – mid November Event in parliament 14th January, by invitation. |
| Governance Group | Continuing to pursue all issues raised in Governance Matters as and when opportunities occur. Would coordinate LINK effort on manifestos and elections at UK, Scottish and Local levels Coordinating LINK Brexit effort Monitoring Lobbying legislative context GG comprises: Brexit Subgroup – this correspondence group has been set up to ensure members are engaged and contributing to LINK work on Brexit as it goes forward Brexit Campaign Steering Group – see opposite Legal strategy subgroup - There is a standing item on the GG agenda for an update from this subgroup. | Brexit – The Governance Group will continue to monitor development and impacts of Brexit. We will do this as LINK and with ELUK and Greener UK colleagues. We will deliver the LINK ‘Fight for Scotland’s Nature’ campaign which will call for a Scottish Environment Act. Through the campaign, LINK aims to raise awareness among the public and decision-makers of the potential impact of Brexit on the environment, fisheries and agriculture. The campaign will focus on (i) environmental principles & governance (ii) framework for future environmental policy (iii) nature protection (future of Birds & Habitats in Scotland) and (iv) post-CAP rural funding and post-CFP fisheries management. The campaign will launch to coincide with ScotGov’s consultation on environmental principles and governance. We will continue to liaise with ScotGov officials on development of statutory instruments. In general, on Brexit and related issues, we will maintain dialogue with relevant Ministers, MPs and MSPs as well as other key decision-makers as necessary. This includes Roseanna Cunningham MSP, Mike Russell MSP, Minister Ian Duncan, Ian Jardine and other Government and elected officials. Legal Strategy Subgroup Environmental rights centre for Scotland – The Legal Strategy Subgroup will pursue the establishment of a centre, with input from a number of individuals who support the case and are willing to support the initiative. Fundraising to coordinate the establishment phase is going ahead. The work involves setting up a SCIO, development of strategy and business plan, a future fundraising strategy and set of policies including case selection criteria. The Subgroup continues to advocate with others for the establishment of environmental courts, not least in relation to the implications of a UK exit from the EU, seeking dialogue with Justice Minister, MSPs and others. Continuing to work through the Scottish Civil Justice Council on policy around Protected Expense Orders. With ELUK, Subgroup monitors UK’s compliance with Aarhus and submits evidence or follows up in ways as needed. | GC: Lloyd Austin RSPB. No VC. RSPB, WWF, SWT, WTS. Brexit Subgroup: RSPB, WWF, WTS, SWT. Mary Church FoES leads Legal Subgroup. FOES, others occ contributing or supporting. Mark Lazarovicz (HF), Guy Linley-Adams (Independent), Ian Cowan, Susan Shaw, Ben Christman. | CO, AM and AOA attend meetings, secretariat by AOA. Much of the GG work programme is directly linked to the AM’s role and thus she is heavily involved with the GG work programme. Miriam Ross recruited Jan 2019 3 days a week as FFSN campaign co-ordinator. President input may be sought for media opportunities surrounding the FFSN Campaign. HFs M Lazarowicz assists on legal strategy subgroup, Andy Myles & James Curran are supportive. Lawyers Ian Cowan and Ben Christman inform the work and this is likely to continue until the centre is established. Seeks DPF support for coordination phase of establishing ERCS. Some DO support for fundraising for the ERCS | Yes, governance issues cut across the work of all groups so we involve others as relevant. On the FFSN campaign, there is liaison with all groups as the campaign messages will highlight LINK issues across the board (Land, Marine, Wildlife). Brexit Subgroup – set up as correspondence group to ensure members engaged and contributing on Brexit as it goes forward. Telecalls are set up monthly to allow any issues to be discussed if needed. Brexit Campaign Subgroup – also a correspondence group set up to take forward the FFSN campaign. Includes members’ communications staff and key policy staff. Legal Strategy subgroup is active and each GG meeting carries an update from this subgroup. | We would like to continue to be represented on Govt’s Environment Strategy fora. No action needed at present as there are already LINK reps on the Envt Strategy External Reference Group. Legal experts (contacts have been made through the legal strategy subgroup and are ongoing) Scottish Universities Legal Network on Europe (SULNE) - good contacts established and communication is as required SCVO – ongoing communication through regular meetings. There is already regular liaison and collaboration with ELUK and Greener UK on Brexit issues. Potential to explore closer working relationship with EEB. Brexit subgroup has sought to make use of IUCN connections to set up meeting on common frameworks with 4 UK administrations. Working with other coalitions on justice and courts issues. | Brexit: All GG members continue to input and monitor Brexit developments. Daphne (to July), Deborah/ Vhairi, Lloyd & Paul Walton are involved in ELUK and Greener UK discussions. They take part in regular ELUK/ GUK calls. All working to ensure that any UK outputs from GUK are devolution-proofed. LINK is continuing to liaise with Government officials on Brexit related issues, in particular in relation to SIs/ SSIs and env’tal principles & governance (EPG). There is regular contact with government officials who work in these areas. LINK submitted its response to the Government’s EPG consultation in May 2019. Via the FFSN campaign: more than 22,000 people called for a Scottish Envt Act. 97 organisations signed our letter to the First Minister, calling for a Scottish Environment Act. 49 MSPs signed our Stand Up for Nature pledge. The ScotGovt Programme for Government went some way towards meeting the asks of campaign, stating an intention to include EU environmental principles and environmental governance measures in the Continuity Bill. A research project brief to explore env governance models was developed, awarded to Prof Campbell Gemmell. A draft version of the report was presented to a workshop of stakeholders and decision-makers on 6/9, the final report & summary published in October 2019. LINK continues to input into Scottish Parliament inquiries on Brexit related issues & provide briefings for MSPs & decision makers. Members of the GG have planned their presence at Autumn party conferences in Oct and Nov to highlight the FFSN campaign & our asks around env governance. There have been meetings with MSPs & good take up of our messages around envtl principles and governance. A roundtable in Parliament 3/4 to discuss env governance issues was attended by 5 MSPs, a Special Adviser & researchers. PQs were asked relating to environment and Brexit; EG one about non-regression principle in relation to keeping pace and envtl standards by Mark Griffin in May, a series of PQs on env governance by Mark Ruskell in July, in October, Claudia Beamish asked what immediate environmental governance mechanisms will be put in place in event of no-deal Brexit. DV spoke to R Cunningham at the April SNP party conference reiterated our asks relating to Environment Act & the FFSN campaign. Vhairi joined a civil society meeting with Michael Russell in Sept and was able to discuss continuity bill, keeping pace and EPG. LINK is seeking further meetings with M Russell and R Cunningham (28/11 in diary with RC) LINK welcomed some parts of the P f G. However, we said it failed to detail steps that will give Scotland’s environment adequate protection from Brexit, with no detail about EPG and whether there would be an independent watchdog. LINK members continue to sit on the Environment Strategy External Reference Group to raise issues relating to envt strategy and EPG. LINK signed a letter to the PM coordinated by the Brexit Civil Society Alliance. It expressed serious concerns about impact of a no-deal Brexit: Communications are ongoing between LINK’s Governance Group & other groups and subgroups about Brexit & related issues. The FFSN campaign is gathering input from all groups & subgroups to develop stories and case studies. GG met Scot Gov officials 1/10 to discuss EPG consultation follow up. Discussed env principles and whether a non-regression principle could be legislated for. Also heard ScotGov’s ideas for various governance models and we reiterated our preference for a Parli Commissioner model. Votes, legislation & processes impacting environmental governance .Progress: The group has been extremely active on env governance issues related to Brexit in past 6 months as above Lobbying regs implementation we will input views to the Lobbying Register review due in early 2020. On agenda for GG meeting 12/11. Legal Strategy Subgroup: Funding was successfully secured to set up the ERCS (Joseph Rowntree; a private donor and DPF). All member bodies were contacted for their support of the ERCS in various ways. Recruitment for 2 3-day week posts of Development Manager & Programme Manager in Sept/Oct. |
| Land Group Vision: Land management which meets SD goals. | The Land Group has an overview and integrating role for the 3 Priority focusses opposite and for the other related Subgroups’ interaction. The Group meets to review this twice a year. | 1. Land ownership and use – influencing land reform to integrate principles of sustainable land use & promoting the LUS. 2. Future of Scottish Agriculture – Influencing the future of rural development funding, post Brexit 3. Mainstreaming Biodiversity – through Species Champions advocacy and pursuance of the NEN and the post-2020 advocacy (see Wildlife below). Meets September and March. | GC Vicki Swales (RSPB), VC Diarmid Hearns NTS Active members – SWT, WTS, RSPB, NTS, SB, Nourish, APRS, Ramblers, SCNP, SWLG, TFL. | Core staff support ongoing for secretariat (DO) AM input needed throughout the year. | The agenda crosses with Planning (land use); Marine and Governance (post-Brexit structures) Priority Subgroups: Land Use & Reform, Food & Farming, Wildlife Others are Woodland Deer, Wildlife Crime, Hilltracks |  | Met 19 September. Subgroups appear to be delivering on their workplans, given finite resources, and government attention in this area limited by Brexit. Subgroups are conscious of connections between their respective strands within the Land group, and of the work of relevant LINK groups elsewhere, e.g. Planning, Governance or Economics. There appear to be no conflicts between these different agendas. Coordination between subgroups is largely coming from shared membership across groups – i.e. member organisations being represented on different subgroups. For the next period, there are opportunities for synergy on: 1) national environmental protections – depending on how Brexit plays out; and 2) on reform of agricultural/forestry subsidies, along with a revitalised Land Use Strategy. For this second strand, there is potential for collaboration outside LINK with land reform advocates, and with the Scottish Land Commission. The Scottish Government recognition of a climate emergency is welcomed, but there is apparently less interest or commitment at government level to biodiversity. There may be a need for LINK to encourage a similar level of SG commitment to nature, in order to drive positive change across the various Land subgroups. Rhetoric from the Conservative government in Westminster may help raise expectations here. More detail in the reports from Subgroups. |
| Marine Group Vision: healthy, well-managed seas, where wildlife is flourishing, ecosystems are protected, connected and thriving, and coastal communities are sustained. | Focussed on securing robust implementation of UK and Scottish legislation with all that entails including the opportunity for recovery of Scotland’s seas to ‘healthy’. | Campaign for effective management of remaining inshore MPAs by securing public support for the measures via an e-action and responding to the Scottish Government consultation expected in early 2019. Secure designation of four outstanding nature conservation MPAs by supporting member led e-actions, responding to the consultation expected in early 2019 and using Save Scottish Seas website and social media channels to raise public support for the sites. Publish briefing report on MPA management framework, using OSPAR criteria, from commissioned work. Publish Seafloor Integrity report 2018 - launched in November 2018 at the MASTS ASM (David Bailey keynote), with corresponding press release and social media (LINK and LINK member channels). Engage with ScotGovt ongoing process to review protection for Priority Marine Features outside of MPAs, including responding to the second consultation on this process expected in early 2019. Engage with the ScotGovt Future of Fisheries management process and upcoming consultations. Engage with ECCLR Committee inquiry into marine issues to secure commitment to address inconsistencies in National Marine Plan and encourage support for a roll out of Regional Marine Plans. Sea Scotland conference Maintain a coordinating role, along with Marine Group members and SNH, on the Sea Scotland steering group to engage decision-makers, marine policy professionals, industry, local communities and other stakeholders in marine planning and wider seas policy. Aquaculture subgroup: Will advocate for tighter regulation of salmon farming in Scotland. Will meet regularly with SEPA following their consultation on the proposed Sector Plan for aquaculture. Will meet regularly with Marine Scotland’s aquaculture team. Will engage, where possible with Marine Scotland’s ‘Farmed Fish Health Framework’ Working Groups and attend meetings of the Working Group on ‘Wild Salmon Interactions’. Will organise meetings with industry, in particular the Scottish Salmon Producers Organisation. Will review SE LINK’s internal policy and advocacy on finfish aquaculture in Scotland. Will develop a joint LINK position on the use of acoustic deterrent devices in Scottish waters. | GC: Calum Duncan (MCS) GVC: Sarah Dolman (WDC) Members: NTS, SWT, RSPB Scotland, WDC, HWDT, RZSS, MCS. (N.B. WWF Scotland now working with reduced capacity on marine with no direct input onto the MG in Scotland). Aquaculture Subgroup leader: Sam Collin SWT Depute: Dawn Purchase MCS Aquaculture Subgroup Members: SWT, MCS, NTS, WDC, HWDT. | Funding for 1 FTE MPEO to end 2019. Core staff involved in admin, HR, fundraising. AM inputs to advocacy strategy and policy development over next 6 months. Species Champ Coordinator will input on relevant aspects | Fisheries work will continue to involve cross over with Governance group and Brexit Subgroup. MPA and PMF work may overlap with Species work of wildlife subgroup. There will be overlap with Species Champion initiative Aquaculture – MBs active there also active cross co-ordination within the MG | Next phase of project work likely to include closer working with marine tourism sector and continuing contact with coastal community groups. Working with ELUK Marine group on UK dolphin and porpoise conservation strategy. In contact about other topics (MPAs etc). Fisheries work – discussion with ELUK staff and G-UK members to ensure consistency of messaging, sometimes joint sign up. Some members may be involved with WCL Plastics position paper, though not directly an MG output. Other allies for environmental sustainability are: Scottish Inshore Fisheries Trust; Scottish Creel Fishermen’s Federation; FFI Marine Community Support Project; Open Seas; COAST; Scottish Fishermen’s Federation and SWFPO. Community Alliance/Planning Aquaculture: SEPA; Marine Scotland; Crown Estate Scotland; Scottish Salmon Producers Organisation Scope to work with England, NI and Wales Links to provide support and advice for aquaculture concerns that arise in England, Wales or Northern Ireland. | Through the late spring and summer, the MG have contributed several major outputs. The MPEO and Convenor worked with ELUK Marine reps to develop a response to the UK Marine Strategy assessment, indicators and targets, along with providing devolved perspectives on several media outputs (including press and social media) expressing disappointment in the UK’s failure to achieve Good Environmental Status for 11 out of 15 indicators. MG members also contributed to Scottish Climate Bill amendments, focusing on blue carbon as a nature-based solution. Sea Scotland conference 2019 was held in June, with several MG members in attendance (two of which are active on the steering group – MCS and RSPB) and helping run workshops. Led by RSPB, the Marine Group produced a collective response to the Scot Govt’s Future of Fisheries Management national discussion paper and the convenor attended Glasgow stakeholder event and gave presentation at the final FFM stakeholder event at Edinburgh Zoo which was held conference-style. A response to the ECCLR Committee’s call for written evidence on the progress of Regional Marine Plans was also submitted, led by SWT. July and August had a major focus on the public consultation detailing proposals for 4 new nature conservation MPAs for mobile species and seabed habitats. Members (MCS/SWT collaborating on one and WDC another) led public campaigns with e-actions, and the Save Scottish Seas platform was used to signpost these campaigns via a new video produced with an MPA Fighting Fund grant. In parallel the Marine Group also engaged in advocacy on North sea cod stock collapse and the repeal of the Windsock cod recovery area, which overlaps with an offshore MPA. Aquaculture: Sam Collin is a member of the Salmon Interactions Working Group. - Dawn Purchase (through MCS) is a member of the Farmed Fish Health Framework – Licensing Working Group. Sam Collin and Richard Luxmoore (now retired) attended the Salmon Interactions Working Group Dawn and Sam attended SEPA workshop on new regulations and waste modelling and a SEPA and Marine Scotland Science workshop on a new wild salmon hazard modelling approach The sub-group and wider Marine Group members have put together a statement on the use of acoustic deterrent devices (and their impact on marine mammals) in preparation for expected discussions with Marine Scotland on this subject. Sam and Richard met Alan Wells at Fisheries Management Scotland to discuss the future management of salmon farming with regards to wild Atlantic salmon and sea trout. |
| Planning Group Vision: that the Scottish land use planning system contributes to a more environmentally sustainable society |  | Close engagement with Planning Bill to its conclusion to ensure it helps contribute to a sustainable Scotland. Taking forward LINK action, including written submissions, a public e-action, coordination of amendments, and liaison meetings. After the Bill passes we will work to influence secondary legislation and the detailed design of implementing the new system. Engagement with the upcoming National Planning Framework 3. The Group is considering a longer term plan to challenge the way the planning system is run. | GC: Aedán Smith RSPB, GVC: Clare Symonds PD Members: RSPB, PD, FoES, SWT, NTS, WTS, APRS, SCNP, SWLG, BSCG, | Ongoing advocacy support from AM, for the Bill and more Secretariat by DO. | Govt’s stated intention is for planning to take on more of a leadership & coordinating role across govt; there is some cross-over to all other groups. Most subgroups are relevant to an extent, particularly Hill Tracks, NEN, Landscape. |  | The Planning Group were very active preparing for Stage 3 at the end of June. The e-action on ERA hosted by FoES was re-activated. Meetings were held with MSPs of all parties on a raft of amendments, and a briefing for the Stage 3 debate. Key amendments on ERA and Hilltracks were unsuccessful (see Hilltracks report), and there were other losses too, primarily on strategic development planning, combination of shift to a 10 year cycle and loss of Main Issues Reporting and regional plans (though regional land use planning subsequently featured in Sept Prog for Govt). Group is scheduling a meeting before the year end to look at next steps. Members and CO contributed to Govt commissioned research for NPF4 over the summer. |
| Deer Subgroup Vision: Ensure sustainable populations of native deer species which play positive roles in Scottish ecosystems & contribute to rural economy |  | Contribute to work of Land Group insofar as deer management is relevant. Contributing to Independent Deer Management enquiry. Evidence and attendance at stakeholder workshops. Preparing for SNH report to ScotGovt on DMG performance Contribute to deer management aspects of forestry strategy/management via LINK and other channels Attend SNH Deer Management Round Table. Timescales: Key milestones in 2019 will be publication of independent review of deer management now expected September, and publication of Deer Management Group progress report expected October. | Duncan Orr-Ewing, Leader MBs: RSPB, NTS, RS, TfL, WTS, JMT. |  | Work sits within the focus of the Land Group and interlinks with LINK work on land management and forestry. We develop consensus around all outputs, usually either face to face or by email. We have a good track record of producing agreed evidence for Parliamentary & other committees, delivering real impact. | Scottish Government, Ministers and Deer Management Enquiry SNH ADMG Forestry Policy Group Routine engagement with SNH (Wildlife Management), Scottish Government (Habitats and Species). | Preparing for publication of DMG assessment, review of Deer Code and Independent Deer Review all expected November 2019 Advocacy lines have been agreed for above. Joint leaflet prepared and will be issued Application to LINK fund for background piece of work on DMG assessment. Meetings held: 21 May SNH Deer Mgt Round Table 29 May SNH Wildlife Management Principles 26 June SNH Wildlife Mgt Principles 3 July ADMG and SNH Meeting |
| Food & Farming Subgroup Vision: Working for sustainable agricultural systems that produce supplies of safe healthy food, protect natural resources & enhance wildlife, habitats & cultural heritage, & provide jobs in rural areas, contributing to a diverse rural economy |  | The Group will: - Continue to develop shared detailed policy positions for post-CAP rural and land use policy. Working with SNH to look in more detail at the impact of funding mechanisms for delivering public goods. - Continue to develop and carry out an advocacy plan for post-CAP policy principles, transition arrangements, and future policy. - Continue to engage with civil servants on transition plans and post-CAP advocacy - Potentially doing something more agenda setting on agro-ecology. Advocacy Strategy: - Set up a series of meetings with MSPs to discuss principles and ideas for post-CAP policy (several have already happened) others in diary). - Continue to advocate for transition arrangements through meetings above. - Make MSPs aware of LINK ‘Stability and Simplicity’ submission - Request a high-level meeting of directors with Fergus Ewing to discuss above issues. | Leader: Pete Ritchie (NS) Depute: Anna Brand. (RSPB) Members: ARC, APRS/SCNP, BESSPG, Bumblebee CT, Butterfly Cons, NTS, PL, RS, SAS, SAGS.SWT, ScotFwag WTS, WWF | Advocacy support from AM will continue to be needed, incl. for MSP and civil servant meetings, letters etc. Potentially a request for DPF depending on outcome of discussions on October 10th. | Members Pete Ritchie, Vicki Swales are on the Land Group. | Good relationship with SLE, Tweed Forum, and other organisations actively involved in Land Use Strategy policy. Good initial discussion at Land Group Workshop in September 2018. No current plans for follow-up. Led session at ELUK conference 10/18 on Sustainable Development Goals with ELUK interest in keeping in touch. Opportunities to engage with WCL during Agriculture Bill process, keeping an eye on Scotland’s position in this. | The key development is the Scottish Government Food and Farming Production Future Policy Group, announced in June Highland Show, on which LINK CO sits, with RSPB, Soil Association, among others. One meeting has been held. The Subgroup’s main focus is feeding into these reps. LINK CO also sits on the Farming 1.5 enquiry sponsored by Nourish and NFUS. This group is getting beyond technical efficiency to the bigger changes needed that are more difficult. There is a new Govt directorate, Sustainable Land Use and Rural Policy, headed by Andrew Scott, to bring forward policies. The Subgroup is involved in an SNH-led project on Preparing the Evidence Base for Post-Brexit Agriculture in Scotland – Case studies on alternative payments. Anna Brand, now left RSPB, was on the steering group. The project aims to analyse the financial situation and public goods delivery of case study farms in each farming sector under both current and future policy and funding scenarios. LINK & RSPB have contributed to the funding of it. We hope this research will show that farmers and crofters can earn comparable amounts of money under a new policy, but will be doing so in exchange for enhanced delivery of environmental public goods. This should provide a robust argument for a public money for public goods approach also being able to underpin farm viability and farmers’ livelihoods, while enhancing environmental outcomes. The subgroup put down a marker on the convergence funding for agriculture that is coming back to Scotland. The aim is to write an open letter, published in the media, detailing how we think that money is best spent, given the climate and nature emergencies. For publication mid-October. |
| Hilltracks Subgroup | In Sept 18 we published a report which evaluated the success of the prior notification system, based on 3 years of monitoring planning authority websites and engaging with stakeholders. Our activities over the following period have been focussed around discussing this report with other stakeholders and building support for our recommendations. | Strategy depends to some extent on outcome of A Wightman MSP’s Stage 3 amendment to the Planning Bill. If successful, the outcome of the amendment would require some monitoring of delivery in future legislation and activities associated with that. If not will pursue our concerns to a forthcoming review of GPDO which the government will be carrying out in late 2019. We need to consider other issues around penetration of landscape by unsightly tracks of various types [wind farms, transmission lines, hydro schemes] and wish to meet with other LINK members and selected externals to inform strategy for action in future. This would involve an assessment of capacity to engage, resources needed, bodies to engage with, and the advocacy around the forthcoming publication of our Recommendations. Should the current campaign not be ultimately successful then our Recommendations (2 Annexes - dealing with improving the current system of prior notification and issues relating to track construction, including those within the planning system) will be used for advocacy in order to effect desirable changes. | Helen Todd & Beryl Leatherland have been Co-Leaders & this will be checked with LINK partners. Members: APRS, BSCG, CC, NTS, NEMT, Ramblers, RSPB, SCNP, SWLG | If support is needed this should be requested by March (or further ahead in the case of the GPDR review) | Relevant to Planning Group and Land Group (via Land use/reform/landscape sub groups) | Politicians, national parks, SG officials, SNH, other organisations outside the LINK network [Mountaineering Scotland, JMT], “opponents” [these can be useful], the general public and the hill-going public, various media as appropriate and as opportunities arise etc We have no definite plans at this stage. We have maintained good relationships with all the above and will endeavour to continue to do so. | Following publication of our report (Sept 2018) and extensive media coverage, an amendment to stage 2 of the Planning Bill was tabled by Andy Wightman MSP on 31 Oct. This wasn’t successful but led to further publicity for the campaign, mainly led by the Scot Green Party, & a commitment by Andy to table another similar amendment at stage 3, again unsuccessful. The minister advised at both stage 2 and 3 debates that the review of permitted development rights which would follow the passage of the bill was a more suitable option to discuss hilltracks regulation. As a result several actions have been progressed: We shared Annex 1 with Andy Wightman and met him to discuss our future options and to ensure we still have his support [we do!] The Annex was shared with David Reekie (SG Planning Dept) and a meeting arranged, which gave a few pointers for future action. Relevant local authority planning authorities have been communicated with, sent Annex 1 and offered a meeting – no success as yet, not even with planners with whom we have some level of engagement, but we may seek to engage with specific LAs at the permitted development review. National Park authorities were sent report. The Revive Coalition Conference in August gave an opportunity to raise the profile of Hilltracks further. Helen & Beryl gave a presentation & responded to questions as part of a panel. There was a great deal of interest in issues around Hilltracks & estates. Subsequent to 2018 report Changing Tracks, we produced two annexes; Annex 1 illustrating the problems & deficiencies of the Prior Notification process &Annex 2 recommending alternative procedures & approaches. Annex 1 was widely circulated but we will reserve Annex 2 to use as an advocacy tool during the PD review process. All Subgroup member have signed up to both Annexes. Continuing to carry out limited monitoring of planning authority websites & respond to members of the public. This activity helps to contribute to maintenance of our case history records. |
| Landscape Subgroup |  | Consider how best to review and promote the Landscape and Wind Energy Statement of 2016 in a suitable context. SNH will organise a half-day workshop to bring MBs and renewable industry reps together to improve mutual understanding and explore common ground in planning for further development of the sector. We have contributed to development of the wider Scottish Landscape Alliance (launch 25/4), to promote landscape interests and raise profile and importance of and commitment to Scottish landscapes. We will evaluate how useful it might be after the launch and formation of its working groups, and consider how we take forward actions and advocacy with them. This is a problem area as several SG areas of interest and policy are relevant and we are aware that maintaining momentum is crucial: LUS, mooted Vision for the Uplands, moorland management, grouse issues, importance to health, tourism, culture, recreation. | Leader: John Thomson Depute: Beryl Leatherland, Members: APRS, NTS, RS, SCNP, SWLG, JMT. Corresponding members: CC, NEMT, SGF HF Bob Aitken attends when available & offers advice. | President could support advocacy. No staff support needed yet, but we may need some support from Advocacy team and officers on a consultation basis, not ongoing | Relevant LINK Groups are Land and Planning, together with the Land Use Subgroup, which also has landscape policy within its brief | Allies: SNH Landscape Institute Scotland (LIS) In future, links with the EEB and IUCN may be appropriate but not ready at this stage. We are aware of a need to be better informed on the landscape and related work and initiatives undertaken by these groups, some feedback from GB interests at the IUCN could be very helpful especially in the short term. | Very much a work in progress at this stage. With the support and participation of our SNH contact Brendan Turvey, we tried to set up a workshop with Scottish Renewables to explore the extent of common ground on renewable energy development ahead of NPF4, but were rebuffed. We are contributing to the Scottish Landscape Alliance and will evaluate how useful this might be after the launch planned for spring 2020. In the meantime, all members are active across the three Working Groups and we have at least one representative in each. Ahead: Scottish Landscape Alliance major event is planned for Spring 2020. |
| Land Reform & Land Use Subgroup Vision: taking a bigger look at these issues in the round | Objectives: Get SG to deliver Policy 7 and Proposal 1 of the LUS - support establishment of regional partnerships and roll out of regional land use frameworks Objective: To ensure that environmental interests and goals receive adequate attention in the implementation and further development of the land reform agenda. Objective: To ensure that landscape interests and goals are adequately recognised in the development of land use thinking and policy, both within LINK and more widely, and are integral to any approaches proposed. | Land Use Strategy: Will pursue contact established with Katriona Carmichael, who is organising a meeting with Welsh reps with experience of taking forward regional land use partnerships. Difficult to predict outcome but LINK members will pursue work programme which brings together action and proposals developed previously across several Groups & Sub-Groups, including Food and Farming, Landscape, & the Planning Group, as well as the Land Use Subgroup. Ideally it will involve both some regional rolling-out of the LUS and some more localised “pathfinder” projects, all designed to illuminate and illustrate during the “transition” period to a post –Brexit regime how a more environmentally benign land use policy might operate. Land Reform: The Subgroup debated the Land Reform Commissions on land ownership concentration at its March 2019 meeting, considering how far its possible for LINK to take a collective view, as opposed to individual members, not resolved. There are some issues for landowning bodies to discuss between themselves, which they will do. Land management is of interest to all. Within the next few months the recommendation is for a bigger LINK discussion around land reform questions on the back of the report. Some analysis of the report is needed first. May require development of a more explicit plan for promoting and defending MB interests. Not clear how much joint effort is needed. Likely to focus on positive elements of the SLC report, than the potentially more problematic (eg mgt of NGO land holdings). The Subgroup will meet Hamish Trench and also MSPs. | Leader: John Thomson Composition of Subgroup will vary with the topic(s) under discussion (Key contributors on land reform are RSPB, NTS, WTS, APRS, SCNP, RS, SAGS; on LUS same plus Buglife, Plantlife & SWT; & on landscape APRS, NTS, SCNP, SWLG. | Ongoing involvement of AM on the advocacy aspects. | The Subgroup reports to the Land Group. Planning and Governance Groups may also be consulted as required. Any work in the field of land value taxation would involve collaboration with the Economics Group. | Targets: Scottish Government, MSPs and Holyrood Committees. Land Commission, SEPA, SNH, NFUS, SLE, potentially Crown Estate Scotland. Allies: The other organisations involved in the stakeholder meeting are all potentially valuable allies, and include bodies such as SLE, who have in the recent past worked constructively with us in this broad field. Ongoing liaison over emerging plans for post-Brexit policy in other parts of the UK will be valuable. The stakeholder meeting highlighted in particular the lessons that could usefully be learned from current practice and emerging thinking in Wales. | Land reform: The Subgroup considered & prepared a response to the Scottish Land Commission’s report on the Scale & Concentration of land ownership, which supported many of its recommendations but countered accusations of poor community engagement on the part of eNGO landowners. It is still too early to say how effective these representations have been in influencing future SG policy & legislative proposals. Land Use Strategy: After a lengthy period of inactivity on SG’s part, the Subgroup urged Ministers to include a commitment to rolling out Regional Land Use Frameworks in the Prog for Govt & was delighted when it appeared in it. At its September meeting it developed ideas for pushing the agenda forward, which it is now pursuing with the Land Commission & SG. A definite success – as far as it goes. Landscape policy: The Sub-Group noted and was kept informed of progress in establishing and taking forward the work of the Scottish Landscape Alliance (launched on 25th April). Members of the Subgroup met ScotGov officials responsible for the Land Reform agenda on 24th June for an update on progress, including the guidance issued on community engagement. They also took the opportunity to underline the need to link the land reform and Land Use Strategy agendas, which have been brought together within the ScotGov staffing structure but have yet to be adequately aligned in practice. John and Deborah met Hamish Trench, CEO Scot Land Commission, on 8/4 to discuss the SLC’s current work programme, relay feedback on the Scale and Concentration of Landownership report & press for co-operation in pursuing roll-out of the Land Use Strategy; an encouraging exchange, revealing considerable common ground & highlighting the scope for further collaboration. Ahead: The Subgroup will organise a workshop to bring together those with experience of and ideas about on-the-ground indicative land use planning and integrated land management with a view to influencing ScotGov thinking about the implementation of the commitment in the PfG. Hamish Trench has indicated that the Land Commission could well be interested in co-operating in arranging and resourcing such an event. Also updating LUS briefing. |
| Wildlife Subgroup Vision: Scotland’s natural heritage (land & sea) is complete in its diversity, with fully functioning ecosystems & resilient to accelerated environmental change. | Species Champions (relevant to all groups) - Liaise with member organisations to determine the priorities for the initiative going forward, to look ahead towards biodiversity target deadlines and to integrate species champions more across the board, eg with the Environment Act campaign and Climate Change bill as it makes its way through parliament. Also have the Species Champion Initiative more involved with the Scottish Youth Parliament and look at sustained funding for the co-ordinator role. Biodiversity post 2020 (relevant to Marine group) - Subgroup to think about what we would like to see for the post 2020 target route map, with a focus placed on the NEN being the framework. Start discussions with key advocacy targets (ie SNH). NEN/Protected Areas (relevant to Land, Planning and Marine Groups)- Create a conceptual map to help visualise the NEN and incorporate the NEN into different sectors, policy areas and bills/acts going through Parliament. Paper to be finalised and submitted on what the NEN is due April. Parliamentary event sponsored by Claudia Beamish MSP for 25 June. Climate Change (relevant to all groups) - The LINK/WWF report Scotland’s Nature on Red Alert published January to influence the Climate Change Bill has been the basis of discussions with various Species Champions MSPs about how they can support that work, and they are keen. |  | Leader: Craig Macadam, Depute: Paul Walton RSPB MBs: ARC, Buglife, BBC, Bat CT, Butterfly Cons, Froglife, MCS, WTS, RSPB, SWT, Plantlife, BES, NTS, RZSS, SBT, TfL, WDC. | Support from: 3-day Species Champions Coordinator Support from Advocacy Officer on secretariat and advocacy Several HFs on mailing list and Subgroup engages with them as necessary on issues. | Species Champions – across the range of LINK groups and subgroups, in support of our asks NEN - Land, Planning and Marine Groups | Audiences: Scottish Government, MSPs, SNH, SEPA. Allies: LINK members, Species Champion MSPs, LBAP officers(?) Species Champions initiative is being operated in Wales and England. We regularly keep an eye on UK (English) initiatives to see how they might interact with our work in Scotland. An example is Michael Gove’s plan for a Nature Recovery Network in England and the parallels with the NEN. | At its last meeting the Subgroup reviewed advocacy priorities in the next 6 - 12 months which are: National Ecological Network (NEN), including work on Protected Areas, Climate Change/Biodiversity Strategy for 2020 and beyond, Biodiversity Route Map and Species Champion initiative. A short life working group for the Climate Bill steered Climate Bill advocacy. In late 2018 members agreed to form a smaller Wildlife Advocacy Working group so immediate priorities could be met timely. WAW first met in May 2019 & then every 3 weeks over Zoom. Progress: Biodiversity: National Ecological Network (NEN): The Subgroup with support from the Advocacy team organised a NEN roundtable event at the parliament 25/6, Nature Connections hosted by Claudia Beamish, the event looked at current examples of ecological network in practice and academia. This was followed by a meeting between Claudia and staff, to discuss next steps on the LINK NEN advocacy WAW is steering development of a public facing NEN resource which will be contracted out to Scottish Big Picture, for which a DPF bid was submitted. LINK supported the launch of the State of Nature report on social media. The Scottish publication was supported by DPF funds. Lewis MacDonald MSP was asked to lodge a motion on the publication of the SoN report. Climate Change Bill: LINK gave evidence to ECCLR on Stage 2 and MSPs briefings for LINK amendments were produced at Stage2 and Stage 3 of the Bill. Species Champion: A review of the initiative was conducted among MBs involved with constructive feedback on what’s working and what needs to be improved, including the need for better communication among LINK, member bodies and MSPs, more structure in forward planning and more guidance on Champions’ engagement, especially as they are increasingly being used in LINK-wide advocacy. From this, a set of project aims, and metrics were produced, the protocol document refreshed and a new document “Making the most out of your Species Champions” produced. Several new Champions joined the initiative over the summer months, making the total now 106 MSPs Championing 112 species. Species Champions have been engaging in LINK-wide work following on from a focus towards more targeted advocacy, including climate, wildlife crime and the Fight for Scotland’s Nature Campaign. Calum Langdale, SC coordinator, left LINK in October. Ahead: CBD (Beijing) and COP (Glasgow) in 2020. Staff exploring what MBs are doing for COPs will further inform the LINK actions in the coming months. |
|  | Wildlife Crime Subgroup of Wildlife Subgroup 1) Considering the response from the Police Scotland lead on Wildlife Crime, Det. Chief Supt Mclean, on questions raised at the February 2019 meeting (still awaited) 2) Supporting the new PAW PDG (Priority Development Group) for badgers, and encouraging both BCT and SWBG to push for similar PDGs for bats and beavers 3) Working towards the proposed LINK round table on Advocacy on Wildlife Crime Prevention, planned for September 2019 4) Co-ordinating action on wildlife crime amongst the various relevant Species Champions, i.e. MSPs for badgers, beavers, bats and freshwater pearl mussels |  | Leader: Eddie Palmer. Depute: Liz Ferrell Members: RSPB, Scottish Badgers, Bat Conservation Trust, SRSG, SWLG, SCRA, WDC, SWBG. | Subgroup keeps in touch with Advocacy Manager over advocacy strategy Otherwise not expected to have to involve any LINK staff |  | Scope to work at UK level not known, as Scotland is ahead of rest of UK in wildlife crime reporting | MBs continued to build relationships with MSP Species Champions. All MSPs were invited to a LINK Parliamentary event 1 Oct Wildlife Crime Prevention: (1999-2019) a 20-year review. Several SCs have engaged where they attend meetings, pledge support, speak up in Parliament, undertake site visits and engage in LINK campaigns. Collaborative working with the National Wildlife Crime Unit: MBs participated in its ‘Undisturbed’ campaign to raise awareness amongst the public, wildlife waters and photographers of the risks and dangers to disturbing wildlife. WDC and BCT involved in campaign to varying degrees through tweets and media campaigns. Seeking collaborative working with Scottish Sentencing Council: The SCS are producing an environmental and wildlife crime sentencing guideline. Subgroup drafted a letter to Stephen O’Rourke QC offering assistance in the production of these guidelines in line with the business plan. We understand that the SCC will undertake a public consultation on a draft guideline, we hope it useful to offer our input early. Organisation of Parliamentary roundtable event: Subgroup successfully organised the event Wildlife Crime Prevention: (1999-2019) a 20-year review for 1 October. MSPs, Parliament officials, SNH and NGOs briefed on wildlife crime issues, the challenges and barriers in effectively reducing and preventing wildlife crime in Scotland as well as exploring the potential solutions with minuted actions to take forward in the coming months. LINK responded to Alison Johnstone’s Consultation on the Proposed Protection and Conservation of Wild Mammals (Scotland) Bill; and the Consultation on Wildlife Crime Penalties Review. Ahead: Subgroup drafted 2 year plan with agreement from all its members to be obtained during January 2020 meeting.. |
|  | Woodland Subgroup of Wildlife Subgroup Next focus of work is the Implementation and Monitoring Framework of the Forestry Strategy between now and Spring 2020. There will be a stakeholder group which LINK would like 2 or 3 NGO places. Two new executive agencies of the Scottish Government deliver forestry and land management functions: Scottish Forestry, which is responsible for regulatory, policy, support and grant-giving forestry functions; and Forestry and Land Scotland, which is responsible for managing the Scottish Ministers' land known as the National Forest Estate. Both will have work plans that will be consulted upon. Woodlands will liaise with the Forest Policy Group, to look at what all want to see in the implementation strategy |  | Leader: Charles Dundas WTS. Depute: Sian Williams RSPB Members: WTS, TfL, RSPB, Plantlife, BCS, NTS, SWT | None |  | Scottish Forestry, Forestry and Land Scotland, Scottish Government, SLE, NFUS. Forest Policy Group. Our concerns are domestic to Scotland. | Forestry Act came into force 1 April. Forest & Land Scotland, the successor to Forest Enterprise, consulted on its corporate plan, unsatisfactory and we submitted a forthright response. Expect a consultation on the plan for the policy and regulatory side soon along similar lines, Its CEO, Jo O Hara will step down at Christmas. The Forestry strategy came into effect on 1 April, minus the action plan and monitoring framework. These are due to be in place by 1 April 2020. This will contain the detail. The first Stakeholder reference group was held during the summer (V Swales attended). It is a blank sheet. MBs have been coming up with ideas and discussions will be extended to the other members of the subgroup, to get some solid and ambitious asks into it. Ahead: November meeting scheduled. |
| Media Forum | Forum for exchange of intel and experience among staff/volunteers across LINK network who deal with media. Builds capacity & aims to influence agenda. | Forum has not met for over a year. | Around 18 MBs The intention is that leadership rotates among those interested | None |  | Media channels, political commentators | There were no meetings. Members of the Forum helped to shape the LINK Media Training Day on 17 September. A meeting of the Forum is scheduled for 6 November. CO convening. |
| Scottish Environment Fundraisers Forum | Facilitate partnership between fundraisers in LINK to share info, experience & under-standing of sources of funding for Scotland’s environment. | Meetings are quarterly, normally with one or two external speakers per meeting from statutory, lottery, Trust, corporate streams, as well as some who can offer fundraising advice, information and support. All MBs with staff with fundraising responsibilities are welcome to participate. Continue to provide funders with opportunity to engage with whole sector rather than individual charities by attending SEFF meetings, therefore reaching a wider cross section of general funding streams and increasing ENGO advocacy opportunities for the environment and for environmental funding. SEFF has commissioned a video (This is Scotland) to take forward the findings of the funders’ report Where the Green Grants Went Scotland and make the case for increased funding to support Scotland’s environmental sector. A steering group was established to take forward advocacy strategy and comms plans. | Leader: Steven Gardner (SWT) Depute: Alison Connolly (RSPB) Minutes: Dianne Laing (SCAPE/AS) Varies. SWT, RSPB, WTS, WWFS, NTS, SB, Froglife, FoES, SCAPE, SAS, TfL, P,life. | DPF support was given towards the video in 2018. Possible support in coordinating the launch and further distribution of the film. |  | Scottish funding bodies (Trusts & Foundations), UK Charitable Trusts, Scottish Government, HLF, BIG, SNH. | Two meetings were held in June and September. SEFF subgroup planned the event This is Scotland, for 10 October where speakers from the Environmental Funders Network, National Lotteries Heritage Fund and LINK discussed the opportunities for environmental funding in Scotland, and launched the film. Attendees were from funding bodies, SNH, LINK members. Ahead: A follow up discussion with SNH, EFN, NLHF and LINK. |

| Work area | Action towards objectives: improvement of national policy and implementation; improved capacity of network to contribute; & effective network. | Specific tasks, targets, timings and indicators of progress where provided | Leader-ship and support | Staff roles/ Funding | Integration within LINK | Wider allies and liaison | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Network meetings 2019 AGM 2018 AGM 2019 | 2 p.a. 9 May & 12 December, updating between members, Groups, Subgroups; horizon scanning aided by PSRs; review priorities; evaluate effort, integration; sometimes with theme. Final prep and circulation of papers for: December 2018- Elect trustees, appoint President & HFs, present annual report & accounts, ratify subscriptions proposal Determine date, advance prep, rotation, appointments. |  | CO with input from Chair and other staff CO & FOM, with Treas & Chair Ditto | Various in the preparation | Across the range of work Part of annual gathering | Occ. invited audience. AGM open to members | The May meeting was well attended and included sessions to input to the next Corporate Strategy, and planning for the next 1-3 years by Groups and Subgroups. |
| Dialogue with LINK Member Bodies | Re-start fresh dialogue from Mid-2019, to inform future LINK strategy (new strategy due mid-2020) and to ensure members’ satisfaction and engagement are understood and concerns are being addressed. | Board dialogue, coordinated by Chief Officer. Incoming CO offering all members an initial meeting Feb/March/April. | CO |  | Aim is contact with every member body over the year of dialogue |  | Deborah continued her programme of meetings with members over the period, the findings have fed into the new LINK Strategy. |
| Congress 2019 | Determine date and theme for annual event for building community among member bodies and informing network on issues of overarching interest. |  | DO with steering group of trustees | Delivered by staff. | Theme stems from key priorities. | Externals invited as relevant to theme. | Congress 17 September was on the theme of Storytelling. The sold out afternoon training session included a keynote speech from Matt Locke, Storythings on Storytelling; followed by workshops on storytelling (Matt & Deborah), films on phones (Catherine Gemmell, MCS), budget social media campaigning (Rebecca Curtis Moss, FoES) & traditional media (Alan McCombes JMT) Over 50 members came to the evening session for dinner and speed talks on successful storytelling on Climate (Mike Robinson), Economics (Matthew Crighton), Marine Litter (Catherine Gemmell) Access/social justice (Helen Todd), followed by general discussion. |
| Fundraising | Ongoing overview and planning for future of core enterprise and of key projects. | Overview via Funding Subgroup for core. CO and DO maintain overview of project needs. Fundraising is ongoing for Marine and ERCS. Reporting to funders. | Several staff & group leads |  |  |  | SNH and SG funding the same rate as last year. SG element confirmed July. Meeting ahead with SG to discuss future core funding Success with application for ERCS to JRCT and a private donor. Applications for Marine and Species Champions posts prepared, outcomes yet unknown. Meeting held September with William Grant Foundation on progress and future funding. Reports prepared for SNH/SG, EFF and WGF. |
| Workshops on topics prioritised by members and/or Board | Scope views on where collective work can address gaps identified by strategic planning. Keep watching brief for topics needing ‘work-shopped’ and add these to plan as agreed. | Land has identified need for wider meeting on Scottish Land Commission’s March report. | Staff organise & pursue as resources allow | Delivered by staff with Group leads. | Open to all members | Topic specific, and for organisers to determine | Circular economy workshop held in September to which members and allies invited. |
| LINK Receptions 2019 | With audiences across the sectors to celebrate work in which we are all involved, providing networking and soft lobbying opportunities. | Scottish Environment Reception in Parliament – Date 5 June. Festive Reception December 2019 – Date 12 December. | AOA & DO | Sponsorship & organisation | Open to all members | Relationship -building | Well attended Environment Reception on 5 June on theme of citizen science, sponsored by SEPA, included handover of FFSN materials to Minister by school children. |
| Strategic liaison | Board / President level development of relationships with wider policy community. | Review at spring 2019 the Board’s thinking on relationships to be developed/nurtured across sectors, players and key bodies | Board, Groups, Staff, with support of HFs and President as needed |  |  | Relationship- building for stronger advocacy. Strengthening eNGO profile. | CO involved in wide range of meetings with key contacts which will feed into new corporate strategy. SNH and LINK Boards meeting due 2/10. SEPA LINK meeting held 19/9. CNPA meeting held August on itss Economic Strategy. |
| LINK’s series of events in Parliament | Programme of events over the year linked to priorities, supported by Advocacy Team. Addressing cross-party parliamentary audiences on issues prioritised by LINK Groups | Up to 4. Topics to be identified. Timing – across the year NEN June Circular Economy June | AOA & AM with input from others |  |  |  | CE event held June. NEN event 25 June. Wildlife Crime event -1 Oct. Ahead: CE event 14 January. |
| Environment Links UK | Federal working with the other 3 Links on UK issues. Informed by MOU and ELUK strategy, this involves regular liaison designed to help each Link improve services & to support all the Links in their relationship building & advocacy at country-level, & with UK and EU audiences. Also connecting with Irish Environmental Network | Federal collaboration on: - Brexit (via ELUK BNC & Greener UK coalition) - Marine (via Links’ marine groups) - Circular Economy, Climate – loosely via staff and some members Directors sharing info and intel on operations, funding, protocols, political contexts | CO, AM, GCs, SGLs & Trustees | Delivered by staff, some Groups players, trustees | Network kept informed of joint initiatives, and progress at strategic level | WCL, NIEL, WEL are the main allies. Irish Environmental N/W | Regular liaison between directors continued via zoom. Also see under Governance and Marine. Chair and CO attending ELUK meeting in Birmingham, October. |
| EEB, IUCN and other international bodies | Use / develop LINK use of these bodies in relation to post-Brexit needs | 2 networking dinner October and November 2018 considered Scottish needs of national and international networks, post-Brexit. Actions emerging from that – to be confirmed. | CO, AM, Trustees, Fellows, President LINK delegates |  |  | Relationship- building for stronger advocacy | CO attended IUCN meeting in Rotterdam early July, and will attend November EEB meeting in Berlin. |